## Sheet1
Document ID | Title | Current Revision | Current Client Revision | Client Document ID | Document Purpose | Client Action | Client Review Status | Discipline | Man Hours | Responsible | Keywords | Client WBS | Document Need Translation | Work Pack ID | IFR Planned | IFR Forecast | IFR Actual | IFU Planned | IFU Forecast | IFU Actual
C5663/CS30/CAL/4500/3101 | Static Calculation - Steel Structure for Main Platform |  |  | 7650-8320-CA-810-3101 | Deliverable | 2 |  | 30 | 80 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS30/CAL/4500/3201 | Static Calculation - Steel Structure for Instrumentation Platform | B | EO2 | 7650-8320-CA-810-3201 | Deliverable | 2 | IN - 3 | 30 | 15 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 | 2022-09-30 | 2023-02-24
C5663/CS30/CAL/4500/3301 | Static Calculation - Steel Structure for PSV nd PVV Platform |  |  | 7650-8320-CA-810-3301 | Deliverable | 2 |  | 30 | 20 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS30/CAL/4500/3401 | Static Calculation - Steel Structure for Diametric Walkway | 1 | EA1 | 7650-8320-CA-810-3401 | Deliverable | 2 | IN - 1 | 30 | 10 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-20 | 2022-09-30 | 2022-09-30 | 2022-10-21
C5663/CS30/CAL/4500/3501 | Static Calculation - Steel Structure for Emergency Escape Ladder | 2 | EF1 | 7650-8320-CA-810-3501 | Deliverable | 2 |  | 30 | 10 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-09 | 2022-09-30 | 2022-09-30 | 2022-10-12
C5663/CS30/CAL/4500/3601 | Static calculation – Steel Structure for Peripheral Handrail around Tank Roof | 2 | EF1 | 7650-8320-CA-810-3601 | Deliverable | 2 | IN - 4 | 30 | 4 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-05 | 2022-09-30 | 2022-09-30 | 2022-09-26
C5663/CS30/CAL/4500/3701 | Static Calculation - Steel Structure for Stair Tower |  |  | 7650-8320-CA-810-3701 | Deliverable | 2 |  | 30 | 20 |  |  | AE301000 | FALSE |  | 2023-10-31 | 2023-10-31 |  | 2023-11-30 | 2023-11-30
C5663/CS30/CAL/4500/3702 | Static Calculation - Lifting of Stair Tower |  |  | 7650-8320-CA-810-3702 | Non-Deliverable | 2 |  | 30 | 20 |  |  | AE301000 | FALSE |  | 2023-10-31 | 2023-10-31 |  | 2023-11-30 | 2023-11-30
C5663/CS30/DWG/4500/3101 | Steel Structure for Main Platform - ISO View and Plan Views |  |  | 7650-8320-46-810-3101 | Deliverable | 2 |  | 30 | 60 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS30/DWG/4500/3102 | Steel Structure for Main Platform - Sections and Details |  |  | 7650-8320-46-810-3102 | Deliverable | 2 |  | 30 | 60 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS30/DWG/4500/3201 | Steel Structure for Instrumentation Platform - ISO View and Plan View | 1 | EA1 | 7650-8320-46-810-3201 | Deliverable | 2 | IN - 1 | 30 | 5 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-17
C5663/CS30/DWG/4500/3202 | Steel Structure for Instrumentation Platform - Sections and Details | 1 | EA1 | 7650-8320-46-810-3202 | Deliverable | 2 | IN - 1 | 30 | 10 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-17
C5663/CS30/DWG/4500/3301 | Steel Structure for PSV and PVV Platform - ISO View and Plan Views |  |  | 7650-8320-46-810-3301 | Deliverable | 2 |  | 30 | 20 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS30/DWG/4500/3302 | Steel Structure for PSV and PVV Platform - Sections and Details |  |  | 7650-8320-46-810-3302 | Deliverable | 2 |  | 30 | 20 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS30/DWG/4500/3401 | Steel Structure for Diametric Walkway - ISO View and Plan Views | 1 | EA1 | 7650-8320-46-810-3401 | Deliverable | 2 | IN - 1 | 30 | 15 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-20 | 2022-09-30 | 2022-09-30 | 2022-10-21
C5663/CS30/DWG/4500/3501 | Steel Structure for Emergency Escape Ladder - Plan Views and Section | 1 | EA1 | 7650-8320-46-810-3501 | Deliverable | 2 | IN - 3 | 30 | 5 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-12 | 2022-09-30 | 2022-09-30 | 2022-10-12
C5663/CS30/DWG/4500/3502 | Steel Structure for Emergency Escape Ladder - Sections and Details | 2 | ES1 | 7650-8320-46-810-3502 | Deliverable | 2 | IN - 4 | 30 | 10 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-12 | 2022-09-30 | 2022-09-30 | 2022-10-12
C5663/CS30/DWG/4500/3601 | Steel Structure for Peripherical Handrail around Tank Roof Plan Views and Details | 1 | EA1 | 7650-8320-46-810-3602 | Deliverable | 2 | IN - 4 | 30 | 3 |  |  | AE300000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-07 | 2022-09-30 | 2022-12-23 | 2022-11-24
C5663/CS30/DWG/4500/3701 | Steel Structure for Stair Tower - ISO View and Plan Views |  |  | 7650-8320-46-810-3701 | Deliverable | 2 |  | 30 | 20 |  |  | AE301000 | FALSE |  | 2023-10-31 | 2023-10-31 |  | 2023-11-30 | 2023-11-30
C5663/CS30/DWG/4500/3702 | Steel Structure for Stair Tower - Sections and Details |  |  | 7650-8320-46-810-3702 | Deliverable | 2 |  | 30 | 20 |  |  | AE301000 | FALSE |  | 2023-10-31 | 2023-10-31 |  | 2023-11-30 | 2023-11-30
C5663/CS30/MTO/0000/3032 | Material Take-off - Outer Tank Structures of Ethane Refrigerated Tank |  |  | 7650-8320-BM-810-3032 | Deliverable | 2 |  | 30 | 16 |  |  | AE302000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS31/CAL/6105/3201 | Drainage System - Calculation Note | A | EO1 | 7650-8310-CA-810-3201 | Deliverable | 2 |  | 31 | 20 |  |  | AE312000 | FALSE |  | 2022-12-21 | 2022-12-21 | 2023-01-26 | 2023-01-31 | 2023-01-31
C5663/CS31/CAL/6105/3501 | Structural Analysis - Foundation for Emergency Escape Ladder | 1 | EA1 | 7650-8310-CA-810-3501 | Deliverable | 2 |  | 31 | 4 |  |  | AE310000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-21 | 2022-09-30 | 2023-01-28 | 2023-01-24
C5663/CS31/CAL/6105/3701 | Structural Analysis - Foundation for Stair Tower |  |  | 7650-8310-CA-810-3701 | Deliverable | 2 |  | 31 | 20 |  |  | AE314000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS31/DWG/6105/3101 | Road and Paving - Layout Drawing |  |  | 7650-8310-45-810-3101 | Deliverable | 2 |  | 31 | 20 |  |  | AE313000 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/CS31/DWG/6105/3102 | Raod and Paving - Profile and Section |  |  | 7650-8310-45-810-3102 | Deliverable | 2 |  | 31 | 40 |  |  | AE313000 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/CS31/DWG/6105/3201 | Drainage System - Layout Drawing | A | EO1 | 7650-8310-45-810-3201 | Deliverable | 2 |  | 31 | 8 |  |  | AE312000 | FALSE |  | 2022-12-21 | 2022-12-21 | 2023-01-26 | 2023-01-31 | 2023-01-31
C5663/CS31/DWG/6105/3202 | Drainage System - Section and Details | A | EO1 | 7650-8310-45-810-3202 | Deliverable | 2 |  | 31 | 40 |  |  | AE312000 | FALSE |  | 2022-12-21 | 2022-12-21 | 2023-01-26 | 2023-01-31 | 2023-01-31
C5663/CS31/DWG/6105/3501 | Formwork Reinforcement and Bar Bending Schedule Foundation for Emergency Escape Ladder | 1 | EA1 | 7650-8310-43-810-3501 | Deliverable | 2 |  | 31 | 4 |  |  | AE310000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-21 | 2022-09-30 | 2023-01-27 | 2023-01-24
C5663/CS31/DWG/6105/3701 | Formwork - Foundation for Stair Tower |  |  | 7650-8310-43-810-3701 | Deliverable | 2 |  | 31 | 20 |  |  | AE314000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS31/DWG/6105/3702 | Reinforcement and Bar bending Schedule - Foundation for Stair Tower |  |  | 7650-8310-43-810-3702 | Deliverable | 2 |  | 31 | 20 |  |  | AE314000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS31/DWG/6105/3703 | Piling Drawing - Foundation for Stair Tower | A | EO1 | 7650-8310-42-810-3703 | Deliverable | 2 |  | 31 | 20 |  |  | AE311000 | FALSE |  | 2022-11-30 | 2023-01-27 | 2023-01-25 | 2022-12-21 | 2023-02-24
C5663/CS31/MTO/4500/3031 | Material Take-off - Outer Tank Civil of Ethane Refrigerated Tank |  |  | 7650-8310-BM-810-3031 | Deliverable | 2 |  | 31 | 20 |  |  | AE314000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS32/ADW/0000/0002 | Plot Plan of Ethane Refrigerated Tank |  |  | 7650-8230-01-810-3002 | Deliverable | 1 |  | 32 | 400 |  |  | AE322884 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-10-31 | 2023-10-31
C5663/CS32/ISO/3700/0001 | Isometric Book |  |  | 7650-8230-IN-810-3001 | Deliverable | 3 |  | 32 | 800 |  |  | AE322874 | FALSE |  | 2023-11-29 | 2023-11-29 |  | 2024-01-31 | 2024-01-31
C5663/CS32/LOD/3700/3021 | Ethane Refridgerated Tank Piping Layout Drawings OSB-TK-1001 | A | EO1 | 7650-8230-56-810-3021 | Deliverable | 3 |  | 32 | 400 |  |  | AE322884 | FALSE |  | 2023-04-28 | 2023-04-28 | 2022-12-23 | 2023-10-31 | 2023-10-31
C5663/CS32/LST/0000/0001 | Line List of Ethane Refrigerated Tank |  |  | 7650-8230-26-810-3020 | Deliverable | 3 |  | 32 | 16 |  |  | AE322000 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/CS32/RPT/3700/0001 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3001 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0002 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3002 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0003 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3003 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0004 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3004 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0005 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3005 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0006 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3006 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0007 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3007 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0008 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3008 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0009 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3009 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS32/RPT/3700/0010 | Pipe Stress Report - xx |  |  | 7650-8230-RP-810-3010 | Deliverable | 2 |  | 32 | 16 |  |  | AE322864 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS33/LOD/3052/0001 | Lighting, Sockets and Local Power Supply Equipment Detailed Layout Tank - Riser and Main Staircase | A | EO1 | 7650-8530-79-810-3009 | Deliverable | 2 | IN - 2 | 33 | 10 |  |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-12-20 | 2022-12-21 | 2023-01-27
C5663/CS33/LOD/3052/0002 | Lighting, Sockets and Local Power Supply Equipment Detailed Layout Tank - Area 02 Diametric, Peripheral Walkway and Main Platform | A | EO1 | 7650-8530-79-810-3010 | Deliverable | 2 | IN - 2 | 33 | 10 |  |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-12-30 | 2022-12-21 | 2023-01-27
C5663/CS33/LOD/3052/0003 | Lighting, Sockets and Local Power Supply Equipment Detailed Layout Tank - Area 03 Diametric, Peripheral Walkway and PSV and PVV Platform | A | EO1 | 7650-8530-79-810-3011 | Deliverable | 2 | IN - 2 | 33 | 10 |  |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-12-28 | 2022-12-21 | 2023-01-27
C5663/CS33/LOD/3052/0004 | Lighting, Sockets and Local Power Supply Equipment Detailed Layout Tank - Emergency Escape Ladder | A | EO1 | 7650-8530-79-810-3012 | Deliverable | 2 | IN - 2 | 33 | 10 |  |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-12-05 | 2022-12-21 | 2023-01-27
C5663/CS33/LOD/3056/3001 | Earthing System - Detailed Underground Earth Electrode/Conductor Layout |  |  | 7650-8530-72-810-3001 | Deliverable | 1 |  | 33 | 10 |  |  | AE335000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/CS33/LOD/3056/3021 | Lightning Protection System - Detiled Layout - Tank |  |  | 7650-8530-72-810-3021 | Deliverable | 1 |  | 33 | 10 |  |  | AE334000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/CS33/LOD/3061/0001 | Electrical Cable Routing Above Ground - Overview/Division Plan |  |  | 7650-8530-78-810-3001 | Deliverable | 2 |  | 33 | 10 |  |  | AE333000 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-05-31 | 2023-05-31
C5663/CS33/LOD/3061/0002 | Electrical Cable Routing Above Ground - Detailed Layout Tank - Riser and Main Staircase |  |  | 7650-8530-78-810-3002 | Deliverable | 2 |  | 33 | 10 |  |  | AE333000 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-05-31 | 2023-05-31
C5663/CS33/LOD/3061/0003 | Electrical Cable Routing Above Ground - Detailed Layout Tank - Main Platform |  |  | 7650-8530-78-810-3003 | Deliverable | 2 |  | 33 | 10 |  |  | AE333000 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-05-31 | 2023-05-31
C5663/CS33/LOD/3061/0004 | Electrical Cable Routing Above Ground - Detailed Layout Tank - PSV and PVV Platform |  |  | 7650-8530-78-810-3004 | Deliverable | 2 |  | 33 | 10 |  |  | AE333000 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-05-31 | 2023-05-31
C5663/CS34/LOD/0000/3005 | Instrument Cable Routing Above Ground - Overview/Division Plan |  |  | 7650-8550-68-810-3005 | Deliverable | 2 |  | 34 | 16 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/CS34/LOD/0000/3006 | Instrument Cable Routing Above Ground - Detailed Layout Tank - Riser and Main Staircase |  |  | 7650-8550-68-810-3006 | Deliverable | 2 |  | 34 | 16 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/CS34/LOD/0000/3007 | Instrument Cable Routing Above Ground - Detailed Layout Tank - Main Platform |  |  | 7650-8550-68-810-3007 | Deliverable | 2 |  | 34 | 16 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/CS34/LOD/0000/3008 | Instrument Cable Routing Above Ground - Detailed Layout Tank - PSV and PVV Platform |  |  | 7650-8550-68-810-3008 | Deliverable | 2 |  | 34 | 16 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/CS34/LOD/3045/3001 | Telecom Equipment (CCTV & PG) Detailed Layout Drawing for Ethane Refrigerated Tank |  |  | 7650-8540-80-810-3001 | Deliverable | 2 |  | 34 | 16 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/CS34/LOD/3200/0001 | Instrument Layout Drawing for Ethane Refrigerated Tank |  |  | 7650-8550-61-810-3001 | Deliverable | 3 |  | 34 | 40 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/TD37/CAL/1900/0001 | Design Calculation for Seismic Design Basis | 1 | EA1 | 7650-8430-CA-810-3001 | Deliverable | 2 | IN - 1 | 37 | 111 | RB4 |  | AE370000 | FALSE |  | 2022-08-30 | 2022-08-30 | 2022-07-26 19:03 | 2022-09-30 | 2022-09-30 | 2022-09-30 11:18
C5663/TD37/CAL/1900/0002 | Design Calculation for Inner Tank | 1 | EA1 | 7650-8430-CA-810-3003 | Deliverable | 2 | IN - 1 | 37 | 111 | RB4 |  | AE370000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-08-08 11:42 | 2022-10-15 | 2022-10-15 | 2022-09-30 11:22
C5663/TD37/CAL/1900/0003 | Design Calculation for Tank Boil-Off | 1 | EA1 | 7650-8430-CA-810-3004 | Deliverable | 2 | IN - 1 | 37 | 111 | NR |  | AE370000 | FALSE |  | 2022-08-30 | 2022-08-30 | 2022-08-29 16:34 | 2022-09-30 | 2022-09-30 | 2022-09-30 11:23
C5663/TD37/CAL/1900/0004 | Design Calculation for Tank Capacity | 1 | EA1 | 7650-8430-CA-810-3002 | Deliverable | 2 | IN - 1 | 37 | 111 | RB4 |  | AE370000 | FALSE |  | 2022-08-30 | 2022-08-30 | 2022-08-03 09:37 | 2022-09-30 | 2022-09-30 | 2022-09-30 15:54
C5663/TD37/CAL/1900/0005 | Design Calculation for Tank Dome Roof Structure | 1 | ES1 | 7650-8430-CA-810-3005 | Deliverable | 2 | IN - 1 | 37 | 111 | NR |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-12-02 11:01 | 2022-12-18 | 2022-12-18 | 2023-01-03 17:34
C5663/TD37/CAL/1900/0006 | Design Calculation for Compression Bar & Roof Anchors | 1 | ES1 | 7650-8430-CA-810-3006 | Deliverable | 2 | IN - 1 | 37 | 111 | NR |  | AE372624 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-30 16:33 | 2022-12-18 | 2022-12-18 | 2023-01-03 17:34
C5663/TD37/CAL/1900/0007 | Design Calculation for Suspended Deck | 1 | ES1 | 7650-8430-CA-810-3007 | Deliverable | 2 |  | 37 | 111 | NR |  | AE372634 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-30 20:05 | 2022-12-18 | 2023-01-27 | 2023-01-19 11:28
C5663/TD37/CAL/1900/0008 | DESIGN CALCULATION FOR WALL LINER |  |  | 7650-8430-CA-810-3008 | Deliverable | 2 |  | 37 | 111 |  |  | AE374106 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/CAL/1900/0012 | Design Calculation for Internal Monorails (Construction & Insulation) | 1 | EA1 | 7650-8430-CA-810-3012 | Deliverable | 2 |  | 37 | 111 | JC5 |  | AE372934 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-12-01 | 2022-12-18 | 2023-01-27 | 2023-01-19 11:28
C5663/TD37/CAL/1900/0014 | Fatique Calculation for Inner Shell / Annular Plate Weld | A | EO1 | 7650-8430-CA-810-3014 | Deliverable | 2 | IN - 1 | 37 | 111 | MT4 |  | AE372614 | FALSE |  | 2022-11-02 | 2022-11-02 | 2022-11-28 11:55 | 2022-11-30 | 2023-01-27
C5663/TD37/CAL/1900/0016 | DESIGN CALCULATION FOR PUMP COLUMN |  |  | 7650-8430-CA-810-3016 | Deliverable | 2 |  | 37 | 111 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/CAL/1900/0017 | DESIGN CALCULATION FOR NOZZLE UTILISATION |  |  | 7650-8430-CA-810-3017 | Deliverable | 2 |  | 37 | 111 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/CAL/6000/0005 | Analysis - Prestressing | 1 | EA1 | 7650-8310-CA-810-3005 | Deliverable | 2 | IN - 1 | 37 | 111 | DS7 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-11-21 08:51 | 2023-03-31 | 2023-03-31 | 2022-12-09 19:38
C5663/TD37/CAL/6000/0006 | Design Calculation - Inner Tank Foundation | 1 | EA1 | 7650-8310-CA-810-3006 | Deliverable | 2 | IN - 1 | 37 | 111 | DS7 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-11-21 08:52 | 2023-03-31 | 2023-03-31 | 2022-12-14 13:09
C5663/TD37/CAL/6000/0009 | Analysis - Liquid Spill | 1 | EA1 | 7650-8310-CA-810-3009 | Deliverable | 2 | IN - 1 | 37 | 111 | JS10 |  | AE372664 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-21 08:52 | 2022-12-18 | 2023-01-27 | 2023-01-11 15:25
C5663/TD37/CAL/6000/0010 | Analysis – Seismic Design of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3010 | Deliverable | 2 | IN - 1 | 37 | 111 | DS7 |  | AE370000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-07-18 13:54 | 2022-09-30 | 2022-09-30 | 2022-08-30 20:15
C5663/TD37/CAL/6000/0011 | Analysis - Blast Wave | 1 | EA1 | 7650-8310-CA-810-3011 | Deliverable | 2 | IN - 1 | 37 | 111 | JS10 |  | AE370000 | FALSE |  | 2022-07-27 | 2022-07-27 | 2022-07-27 19:20 | 2022-09-15 | 2022-09-15 | 2022-08-30 20:15
C5663/TD37/CAL/6000/0013 | Analysis - Construction Stages Wall / Roof |  |  | 7650-8310-CA-810-3013 | Deliverable | 2 |  | 37 | 111 |  |  | AE372654 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/CAL/6000/0014 | Analysis - Impact of Flying Objects | 1 | EF1 | 7650-8310-CA-810-3014 | Deliverable | 2 | IN - 4 | 37 | 111 | DS7 |  | AE372664 | FALSE |  | 2023-01-31 | 2023-01-31 | 2022-11-21 08:52 | 2023-02-28 | 2023-02-28 | 2022-12-14 13:09
C5663/TD37/CAL/6000/0015 | Design Calculation – Working Piles of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3015 | Deliverable | 2 | IN - 1 | 37 | 111 | FZ1 |  | AE370000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-07-25 18:36 | 2022-09-30 | 2022-09-30 | 2022-08-12 08:55
C5663/TD37/CAL/6000/0016 | Design Calculation – Vertical Test Piles of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3016 | Deliverable | 2 | IN - 1 | 37 | 111 | FZ1 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-25 18:52 | 2022-09-30 | 2022-09-30 | 2022-08-12 08:55
C5663/TD37/CAL/6000/0017 | Design Calculation – Horizontal Test Piles of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3017 | Deliverable | 2 | IN - 1 | 37 | 111 | FZ1 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-07-26 10:21 | 2022-09-30 08:55 | 2022-09-30 08:55 | 2022-08-12 08:55
C5663/TD37/CAL/6000/0018 | Analysis - Adjacent Tank Fire | 1 | EF1 | 7650-8310-CA-810-3018 | Deliverable | 2 |  | 37 | 111 | JS10 |  | AE372664 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-03 22:13 | 2023-01-31 | 2023-01-31 | 2023-01-27 13:01
C5663/TD37/CAL/6000/0019 | Analysis - Valve Fire | 1 |  | 7650-8310-CA-810-3019 | Deliverable | 2 |  | 37 | 111 | JS10 |  | AE372654 | FALSE |  | 2023-01-31 | 2023-01-31 | 2023-01-03 22:14 | 2023-02-28 | 2023-02-28 | 2023-01-27 13:01
C5663/TD37/CAL/6000/1012 | Design Calculation – Base Slab of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3012 | Deliverable | 2 | IN - 1 | 37 | 111 | FZ1 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 18:44 | 2022-09-30 | 2022-09-30 | 2022-10-14 10:14
C5663/TD37/CAL/6000/1013 | Design Calculation - Wall of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3113 | Deliverable | 2 | IN - 1 | 37 | 111 | FZ1 |  | AE372664 | FALSE |  | 2023-01-03 | 2023-01-03 | 2022-11-09 12:33 | 2023-01-31 | 2023-01-31 | 2022-11-30 16:25
C5663/TD37/CAL/6000/1014 | Design Calculation - Eaves Beam and Dome Roof of Ethane Refrigerated Tank |  |  | 7650-8310-CA-810-3114 | Deliverable | 2 |  | 37 | 111 |  |  | AE372654 | FALSE |  | 2023-03-31 | 2023-03-31 |  | 2023-04-28 | 2023-04-28
C5663/TD37/DSH/0000/1001 | Datasheet - Ethane Refrigerated Tank OSB-TK-1001 | 1 | EA1 | 7650-8430-DS-810-3002 | Deliverable | 2 | IN - 1 | 37 | 74 | MT4 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 11:37 | 2022-09-30 | 2022-09-30 | 2022-09-29
C5663/TD37/DWG/1900/1001 | Overall General Arrangement of Ethane Refrigerated Tank - 10 - Ethane Storage Tank | 1 | EA1 | 7650-8430-14-810-3020 | Deliverable | 2 | IN - 1 | 37 | 37 | PA |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-25 | 2022-09-30 | 2022-09-30 | 2022-09-29
C5663/TD37/DWG/1900/3002 | Tank Interface | 1 | EA1 | 7650-8430-14-810-3002 | Deliverable | 2 | IN - 4 | 37 | 37 | PA |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-01 | 2022-09-30 | 2022-09-30 | 2022-09-29
C5663/TD37/DWG/1900/3003 | Tank Foundation Loading | 1 | ES1 | 7650-8430-14-810-3003 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-01 | 2022-09-30 | 2022-09-30 | 2022-10-20
C5663/TD37/DWG/1900/3004 | Nozzle Arrangement | A | EO1 | 7650-8430-14-810-3004 | Deliverable | 2 | IN - 4 | 37 | 37 | PA |  | AE372604 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-09 | 2022-12-18 | 2023-01-27
C5663/TD37/DWG/1900/3005 | Roof and Nozzle Orientation | A | EO1 | 7650-8430-14-810-3005 | Deliverable | 2 | IN - 4 | 37 | 37 | PA |  | AE372604 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-01 | 2022-12-18 | 2023-01-27
C5663/TD37/DWG/1900/3101 | OUTER TANK / LINER ORIENTATION |  |  | 7650-8430-14-810-3101 | Deliverable | 2 |  | 37 | 37 |  |  | AE374106 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3102 | OUTER TANK / LINER STRETCH OUT |  |  | 7650-8430-14-810-3102 | Deliverable | 2 |  | 37 | 37 |  |  | AE374106 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3103 | Outer Tank / Liner Bottom Plates | A | EO1 | 7650-8430-14-810-3103 | Deliverable | 2 |  | 37 | 37 | PA |  | AE374106 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-09 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3107 | WALL LINER EMBEDMENTS |  |  | 7650-8430-14-810-3107 | Deliverable | 2 |  | 37 | 37 |  |  | AE374106 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3108 | WALL LINER PLATES |  |  | 7650-8430-14-810-3108 | Deliverable | 2 |  | 37 | 37 |  |  | AE374106 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3201 | Roof General Arrangement | 1 | ES1 | 7650-8430-14-810-3201 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-21 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3202 | Compression Ring Support | 1 | ES1 | 7650-8430-14-810-3202 | Deliverable | 2 | IN - 4 | 37 | 37 | BA3 |  | AE372624 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-21 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3203 | Compression Ring and Bar | 1 | ES1 | 7650-8430-14-810-3203 | Deliverable | 2 | IN - 4 | 37 | 37 | WG2 |  | AE372624 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-10-20 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3204 | Compression Ring and Bar Weld Studs | 1 | ES1 | 7650-8430-14-810-3204 | Deliverable | 2 | IN - 4 | 37 | 37 | WG2 |  | AE372624 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-10-24 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3205 | Compression Bar Anchors | 1 | ES1 | 7650-8430-14-810-3205 | Deliverable | 2 | IN - 4 | 37 | 37 | WG2 |  | AE372624 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-30 16:32 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3206 | Centre Ring | 1 | ES1 | 7650-8430-14-810-3206 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-07 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3207 | Polar Beams | 1 | ES1 | 7650-8430-14-810-3207 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-16 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3208 | Laterals | 1 | ES1 | 7650-8430-14-810-3208 | Deliverable | 2 | IN - 4 | 37 | 37 | BA3 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-10-31 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3209 | Polar Beam to Compression Ring Connection | A | EO1 | 7650-8430-14-810-3209 | Deliverable | 2 |  | 37 | 37 | BA3 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-12-19 | 2022-12-18 | 2023-01-27
C5663/TD37/DWG/1900/3210 | Roof Plates | 1 | ES1 | 7650-8430-14-810-3210 | Deliverable | 2 | IN - 4 | 37 | 37 | WG2 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-29 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3211 | Roof Weld Studs | 1 | ES1 | 7650-8430-14-810-3211 | Deliverable | 2 | IN - 4 | 37 | 37 | WG2 |  | AE374108 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-10-31 | 2022-12-18 | 2022-12-18 | 2022-12-12
C5663/TD37/DWG/1900/3213 | NOZZLE THERMAL DISTANCE |  |  | 7650-8430-14-810-3213 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3214 | NOZZLE REPADS |  |  | 7650-8430-14-810-3214 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3215 | NOZZLE WELD STUDS |  |  | 7650-8430-14-810-3215 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3216 | Construction Monorail | 1 | ES1 | 7650-8430-14-810-3216 | Deliverable | 2 | IN - 4 | 37 | 37 | RP2 |  | AE372934 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-10-30 | 2022-12-18 | 2022-12-18 | 2022-12-14
C5663/TD37/DWG/1900/3217 | Insulation Monorail | 1 | ES1 | 7650-8430-14-810-3217 | Deliverable | 2 | IN - 4 | 37 | 37 | RP2 |  | AE372934 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-10-30 | 2022-12-18 | 2022-12-18 | 2022-12-14
C5663/TD37/DWG/1900/3301 | SUSPENDED DECK ORIENTATION |  |  | 7650-8430-14-810-3301 | Deliverable | 2 |  | 37 | 37 |  |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3302 | Suspended Deck Plates | A | EO1 | 7650-8430-14-810-3302 | Deliverable | 2 |  | 37 | 37 | PA |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-10 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3303 | SUSPENDED DECK STIFFENERS AND HANGERS |  |  | 7650-8430-14-810-3303 | Deliverable | 2 |  | 37 | 37 |  |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3304 | Suspended Deck Splash Ring | A | EO1 | 7650-8430-14-810-3304 | Deliverable | 2 |  | 37 | 37 | BH3 |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-18 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3305 | Suspended Deck Sleeves | A | EO1 | 7650-8430-14-810-3305 | Deliverable | 2 |  | 37 | 37 | PA |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-18 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3306 | Suspended Deck Vents / Equilibrium | A | EO1 | 7650-8430-14-810-3306 | Deliverable | 2 |  | 37 | 37 | RP2 |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-18 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3307 | Suspended Deck Closure Plates | A | EO1 | 7650-8430-14-810-3307 | Deliverable | 2 |  | 37 | 37 | PA |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-25 21:34 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3308 | Suspended Deck Manways | A | EO1 | 7650-8430-14-810-3308 | Deliverable | 2 |  | 37 | 37 | RP2 |  | AE372634 | FALSE |  | 2023-01-03 | 2023-01-03 | 2023-01-18 | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3410 | Inner Tank Orientation | 1 | ES1 | 7650-8430-14-810-3410 | Deliverable | 2 | IN - 4 | 37 | 37 | PA |  | AE372614 | FALSE |  | 2022-11-02 | 2022-11-02 | 2022-11-09 | 2022-11-30 | 2022-11-30 | 2022-12-12
C5663/TD37/DWG/1900/3411 | INNER TANK STRETCH-OUT |  |  | 7650-8430-14-810-3411 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3412 | Inner Tank Bottom Plates | 1 | ES1 | 7650-8430-14-810-3412 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE372614 | FALSE |  | 2022-11-02 | 2022-11-02 | 2022-11-11 18:14 | 2022-11-30 | 2022-11-30 | 2022-12-14
C5663/TD37/DWG/1900/3413 | INNER TANK SHELL | A | EO1 | 7650-8430-14-810-3413 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE372614 | FALSE |  | 2022-11-02 | 2022-11-02 | 2022-11-10 | 2022-11-30 | 2023-01-27
C5663/TD37/DWG/1900/3414 | INNER TANK STIFFENERS |  |  | 7650-8430-14-810-3414 | Deliverable | 2 |  | 37 | 37 | BH3 |  | AE372614 | FALSE |  | 2022-11-02 | 2023-01-27 |  | 2022-11-30 | 2023-02-24
C5663/TD37/DWG/1900/3415 | TEMPORARY DOOR SHEET STIFFENING INNER TANK |  |  | 7650-8430-14-810-3415 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2022-11-02 | 2023-01-27 |  | 2022-11-30 | 2023-02-24
C5663/TD37/DWG/1900/3501 | INNER TANK PLATFORMS AND LADDERS GENERAL ARRANGEMENT |  |  | 7650-8430-14-810-3501 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3502 | SUSPENDED DECK PLATFORM |  |  | 7650-8430-14-810-3502 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3503 | INNER TANK PLATFORM UPPER |  |  | 7650-8430-14-810-3503 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3504 | INNER TANK PLATFORM LEFT HAND |  |  | 7650-8430-14-810-3504 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3505 | INNER TANK PLATFORM RIGHT HAND |  |  | 7650-8430-14-810-3505 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3506 | INNER TANK AND ANNULAR PLATFORM COMMON DETAILS |  |  | 7650-8430-14-810-3506 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3507 | INNER TANK LADDERS |  |  | 7650-8430-14-810-3507 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3508 | INNER TANK PLATFORM GRATING |  |  | 7650-8430-14-810-3508 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3509 | ANNULAR PLATFORMS & LADDERS - GENERAL ARRANGEMENT |  |  | 7650-8430-14-810-3509 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3510 | ANNULAR PLATFORM LEFT HAND |  |  | 7650-8430-14-810-3510 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3511 | ANNULAR PLATFORM RIGHT HAND |  |  | 7650-8430-14-810-3511 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3512 | ANNULAR LADDERS |  |  | 7650-8430-14-810-3512 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3513 | ANNULAR PLATFORM GRATING |  |  | 7650-8430-14-810-3513 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3601 | NOZZLE CONFIGURATION |  |  | 7650-8430-14-810-3601 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3602 | M1 DOME MANWAY (EQUIPMENT) |  |  | 7650-8430-14-810-3602 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3603 | M3 DOME MANWAY (PERSONNEL) |  |  | 7650-8430-14-810-3603 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3605 | NOZZLE N1 FEED INLET |  |  | 7650-8430-14-810-3605 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3606 | NOZZLE N4 & N5 ETHANE IN-TANK EXPORT PUMP OSB-P-1003A & B |  |  | 7650-8430-14-810-3606 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3607 | NOZZLE N13 TO N15 ETHANE IN-TANK TRANSFER PUMP OSB-P-1001A TO C |  |  | 7650-8430-14-810-3607 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3608 | NOZZLE N22 GAS OUTLET |  |  | 7650-8430-14-810-3608 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3609 | NOZZLE N23 PUMP KICKBACK |  |  | 7650-8430-14-810-3609 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3610 | NOZZLE N24 CONDENSATE RETURN |  |  | 7650-8430-14-810-3610 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3611 | NOZZLE N25 BLOWDOWN |  |  | 7650-8430-14-810-3611 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3612 | NOZZLE N26 COOLDOWN SPRAY RING |  |  | 7650-8430-14-810-3612 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3613 | NOZZLE N27 PSV TO FLARE |  |  | 7650-8430-14-810-3613 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3614 | NOZZLE N28 PSV PILOT |  |  | 7650-8430-14-810-3614 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3615 | NOZZLE N29 TO N34 PRESSURE VACUUM VALVE |  |  | 7650-8430-14-810-3615 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3616 | NOZZLE N35 INNER TANK PURGE |  |  | 7650-8430-14-810-3616 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3617 | NOZZLE N36 PSV TO ATMOSPHERE |  |  | 7650-8430-14-810-3617 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3618 | NOZZLE N37 PSV PILOT |  |  | 7650-8430-14-810-3618 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3619 | NOZZLE N38 NITROGEN INJECTION |  |  | 7650-8430-14-810-3619 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3620 | NOZZLE N40 TO N42 PRESSURE CONNECTION |  |  | 7650-8430-14-810-3620 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3621 | NOZZLE V1 EMERGENCY VENT |  |  | 7650-8430-14-810-3621 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3622 | NOZZLE V2 & V3 ANNULAR PURGE |  |  | 7650-8430-14-810-3622 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3623 | NOZZLE T1 & T2 MULTI POINT TEMPERATURE INDICATOR |  |  | 7650-8430-14-810-3623 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3624 | NOZZLE T3 TEMPERATURE INDICATOR - DOME SPACE |  |  | 7650-8430-14-810-3624 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3625 | NOZZLE T4 & T5 RTD CONNECTIONS |  |  | 7650-8430-14-810-3625 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3626 | NOZZLE L1 LEVEL DENSITY (LTD) |  |  | 7650-8430-14-810-3626 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3627 | NOZZLE L2 & L3 LEVEL GAUGE (RADAR) |  |  | 7650-8430-14-810-3627 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3628 | NOZZLE L4 & L5 LEVEL GAUGE (SERVO) |  |  | 7650-8430-14-810-3628 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/1900/3650 | NOZZLE N26 COOLDOWN SPRAY RING INTERNAL DETAILS |  |  | 7650-8430-14-810-3650 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3651 | NOZZLE N35 INNER TANK PURGE INTERNAL DETAILS |  |  | 7650-8430-14-810-3651 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3652 | NOZZLE V1 EMERGENCY VENT INTERNAL DETAILS |  |  | 7650-8430-14-810-3652 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3653 | NOZZLE V2 & V3 ANNULAR PURGE INTERNAL DETAILS |  |  | 7650-8430-14-810-3653 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3654 | NOZZLE T1 & T2 MULTI POINT TEMPERATURE INDICATOR INTERNAL DETAILS |  |  | 7650-8430-14-810-3654 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3655 | NOZZLE L1 LEVEL DENSITY (LTD) INTERNAL DETAILS |  |  | 7650-8430-14-810-3655 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3656 | NOZZLE L2 & L3 LEVEL GAUGE (RADAR) INTERNAL DETAILS |  |  | 7650-8430-14-810-3656 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3657 | NOZZLE L4 & L5 LEVEL GAUGE (SERVO) INTERNAL DETAILS |  |  | 7650-8430-14-810-3657 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3660 | RTD LAYOUT |  |  | 7650-8430-14-810-3660 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3661 | NOZZLE GUIDES AND SUPPORTS |  |  | 7650-8430-14-810-3661 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3662 | PUMP COULMN NOZZLE GUIDES AND SUPPORTS |  |  | 7650-8430-14-810-3662 | Deliverable | 2 |  | 37 | 37 |  |  | AE372934 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3704 | INSULATION SUSPENDED DECK |  |  | 7650-8430-14-810-3704 | Deliverable | 2 |  | 37 | 37 |  |  | AE372634 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3705 | INSULATION DETAILS NOZZLES |  |  | 7650-8430-14-810-3705 | Deliverable | 2 |  | 37 | 37 |  |  | AE372634 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3706 | INSULATION TANK GENERAL ARRANGEMENT |  |  | 7650-8430-14-810-3706 | Deliverable | 2 |  | 37 | 37 |  |  | AE372634 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3801 | NAMEPLATE TANK |  |  | 7650-8430-14-810-3801 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3802 | NAMEPLATE PUMP COLUMN |  |  | 7650-8430-14-810-3802 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3803 | TANK EARTHING |  |  | 7650-8430-14-810-3803 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3804 | Outline Construction Sequence | 1 | EA1 | 7650-8430-14-810-3804 | Deliverable | 2 | IN - 4 | 37 | 37 | BH3 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-07 | 2022-09-30 | 2022-09-30 | 2022-10-12
C5663/TD37/DWG/1900/3805 | PREFABRICATION DRAWING FOR TANK SHELL PLATES |  |  | 7650-8430-14-810-3805 | Deliverable | 2 |  | 37 | 37 |  |  | AE372612 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3806 | PREFABRICATION DRAWING FOR INNER ANNULAR PLATES |  |  | 7650-8430-14-810-3806 | Deliverable | 2 |  | 37 | 37 |  |  | AE372612 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3901 | CUTTING SKETCHES FOR LOW TEMPERATURE MATERIAL |  |  | 7650-8430-14-810-3901 | Deliverable | 2 |  | 37 | 37 |  |  | AE372612 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2022-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3902 | CUTTING SKETCHES FOR CARBON STEEL |  |  | 7650-8430-14-810-3902 | Deliverable | 2 |  | 37 | 37 |  |  | AE374106 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/1900/3903 | CUTTING SKETCHES FOR ALUMINIUM |  |  | 7650-8430-14-810-3903 | Deliverable | 2 |  | 37 | 37 |  |  | AE372610 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/DWG/1900/3904 | CUTTING SKETCHES FOR STAINLESS STEEL |  |  | 7650-8430-14-810-3904 | Deliverable | 2 |  | 37 | 37 |  |  | AE372610 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/DWG/6000/0201 | Civil Design - General Notes | 1 | EA1 | 7650-8310-39-810-3001 | Deliverable | 2 | IN - 1 | 37 | 37 | JH16 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-10-27 | 2023-03-31 | 2023-03-31 | 2022-11-28 15:27
C5663/TD37/DWG/6000/0203 | Prestressing Drawing - General Tendon Arrangement Part 1 | 1 | EA1 | 7650-8310-44-810-3023 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-10-28 | 2023-03-31 | 2023-03-31 | 2022-11-28 15:27
C5663/TD37/DWG/6000/0204 | Prestressing Drawing - General Tendon Arrangement Part 2 | 1 | EA1 | 7650-8310-44-810-3024 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-10-28 | 2023-03-31 | 2023-03-31 | 2022-11-28 15:28
C5663/TD37/DWG/6000/0205 | Prestressing Drawing - General Tendon Accessoires Part 1 | 1 | ER1 | 7650-8310-44-810-3025 | Deliverable | 2 | IN - 1 | 37 | 19 | CG1 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-10-28 | 2023-03-31 | 2023-03-31 | 2022-12-02
C5663/TD37/DWG/6000/0206 | Prestressing Drawing - General Tendon Accessoires Part 2 | 1 | ER1 | 7650-8310-44-810-3026 | Deliverable | 2 | IN - 1 | 37 | 18 | CG1 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-11-02 08:47 | 2023-03-31 | 2023-03-31 | 2022-12-02
C5663/TD37/DWG/6000/1001 | ETHANE REFRIGERATED TANK - CIVIL GENERAL ARRANGEMENT - 10 - ETHANE STORAGE AREA | 1 | EA1 | 7650-8310-43-810-3020 | Deliverable | 2 | IN - 1 | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-08-30 11:05 | 2022-08-30 11:05 | 2022-07-18 11:05 | 2022-09-30 08:57 | 2022-09-30 08:57 | 2022-08-12 08:57
C5663/TD37/DWG/6000/1002 | ETHANE REFRIGERATED TANK - PILE FOUNDATION & COLUMN LAYOUT - 10 - ETHANE STORAGE AREA | 1 | EA1 | 7650-8310-43-810-3021 | Deliverable | 2 | IN - 1 | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-07-18 11:04 | 2022-07-18 11:04 | 2022-07-18 11:04 | 2022-08-10 | 2022-08-10 | 2022-08-10
C5663/TD37/DWG/6000/1003 | ETHANE REFRIGERATED TANK - RAFT GENERAL ARRANGEMENT - 10 - ETHANE STORAGE AREA | 1 | EA1 | 7650-8310-43-810-3022 | Deliverable | 2 | IN - 1 | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-08-31 11:04 | 2022-08-31 11:04 | 2022-07-18 11:04 | 2022-09-30 | 2022-09-30 | 2022-08-10
C5663/TD37/DWG/6000/1004 | ETHANE REFRIGERATED TANK - WALL & BUTTRESS GENERAL ARRANGEMENT - 10 - ETHANE STORAGE AREA | 1 | EA1 | 7650-8310-43-810-3023 | Deliverable | 2 | IN - 1 | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-08-31 11:03 | 2022-08-31 11:03 | 2022-07-18 11:03 | 2022-09-30 | 2022-09-30 | 2022-08-10
C5663/TD37/DWG/6000/1005 | ETHANE REFRIGERATED TANK - EAVES BEAM & ROOF DOME GENERAL ARRANGEMENT - 10 - ETHANE STORAGE AREA | 1 | EA1 | 7650-8310-43-810-3024 | Deliverable | 2 | IN - 1 | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-07-18 11:02 | 2022-07-18 11:02 | 2022-07-18 11:02 | 2022-08-12 08:56 | 2022-08-12 08:56 | 2022-08-12 08:56
C5663/TD37/DWG/6000/1301 | ETHANE REFRIGERATED TANK PILE FOUNDATION: TEST PILE LOCATION LAYOUT - 10 - ETHANE STORAGE AREA | 3 | EA3 | 7650-8310-42-810-3301 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-07-25 18:57 | 2022-09-30 | 2022-09-30 | 2022-08-10
C5663/TD37/DWG/6000/1302 | Ethane Refrigerated Tank Pile Foundation: Vertical Test Pile - 10 - Ethane Storage Area | 2 | EA2 | 7650-8310-42-810-3302 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-07-25 18:57 | 2022-09-30 08:56 | 2022-09-30 08:56 | 2022-08-12 08:56
C5663/TD37/DWG/6000/1303 | Ethane Refrigerated Tank Pile Foundation: Horizontal Test Pile - 10 - Ethane Storage Area | 2 | EA2 | 7650-8310-42-810-3303 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-09-10 18:57 | 2022-09-10 18:57 | 2022-07-25 18:57 | 2022-09-30 08:56 | 2022-09-30 08:56 | 2022-08-10
C5663/TD37/DWG/6000/1310 | ETHANE REFRIGERATED TANK PILE FOUNDATION: BORED PILE FOR RIM AREA - 10 - ETHANE STORAGE AREA | 2 | EA2 | 7650-8310-42-810-3310 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-07-25 18:57 | 2022-09-30 | 2022-09-30 | 2022-08-10
C5663/TD37/DWG/6000/1311 | ETHANE REFRIGERATED TANK PILE FOUNDATION: BORED PILE FOR CENTER AREA - 10 - ETHANE STORAGE AREA | 2 | EA2 | 7650-8310-42-810-3311 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-07-25 18:57 | 2022-09-30 | 2022-09-30 | 2022-08-10
C5663/TD37/DWG/6000/1312 | ETHANE REFRIGERATED TANK PILE FOUNDATION: COLUMN FOR RIM AREA - 10 - ETHANE STORAGE AREA | 2 | EA2 | 7650-8310-42-810-3312 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-07-25 18:56 | 2022-07-25 18:56 | 2022-07-25 18:56 | 2022-08-10 | 2022-08-10 | 2022-08-10
C5663/TD37/DWG/6000/1313 | ETHANE REFRIGERATED TANK PILE FOUNDATION: COLUMN FOR CENTER AREA - 10 - ETHANE STORAGE AREA | 2 | EA2 | 7650-8310-42-810-3313 | Deliverable | 2 |  | 37 | 37 | SF3 |  | AE370000 | FALSE |  | 2022-07-25 18:53 | 2022-07-25 18:53 | 2022-07-25 18:53 | 2022-08-10 | 2022-08-10 | 2022-08-10
C5663/TD37/DWG/6000/2102 | GENERAL ARRANGEMENT DRAWING - TANK BASE SLAB- FORMWORK DRAWING - DETAILS AND SECTIONS |  |  | 7650-8310-44-810-3202 | Deliverable | 2 |  | 37 | 37 |  |  | AE372684 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/2103 | GENERAL ARRANGEMENT DRAWING -TANK BASE SLAB: CONSTRUCTION JOINTS AND POURING SEQUENCE | 1 | ER1 | 7650-8310-44-810-3203 | Deliverable | 2 | IN - 1 | 37 | 37 | JH16 |  | AE372684 | FALSE |  | 2023-03-03 | 2023-03-03 | 2022-11-07 | 2023-03-31 | 2023-03-31 | 2022-12-02
C5663/TD37/DWG/6000/2201 | Prestressing Drawing - Tank Base Slab Vertical Bottom Tendon - Wall | A | EO1 | 7650-8310-44-810-3204 | Deliverable | 2 |  | 37 | 37 | CG1 |  | AE372684 | FALSE |  | 2023-03-03 | 2023-03-03 | 2023-01-11 | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/2202 | Prestressing Drawing - Tank Base Slab Vertical Bottom Tendon - Buttress | A | EO1 | 7650-8310-44-810-3205 | Deliverable | 2 |  | 37 | 18 | CG1 |  | AE372684 | FALSE |  | 2023-03-03 | 2023-03-03 | 2023-01-11 | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/2401 | Ethane Refrigerated Tank - Tank Base Slab - Bottom Reinforcement Plan Part 1 | 1 | EA1 | 7650-8310-44-810-3401 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2402 | Ethane Refrigerated Tank - Tank Base Slab - Bottom Reinforcement Plan Part 2 | 1 | EA1 | 7650-8310-44-810-3402 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2403 | Ethane Refrigerated Tank - Tank Base Slab - Bottom Reinforcement Bar Bending Schedule | 1 | EA1 | 7650-8310-44-810-3403 | Deliverable | 2 | IN - 4 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2404 | Ethane Refrigerated Tank - Tank Base Slab - Top Reinforcement Plan Part 1 | 1 | EA1 | 7650-8310-44-810-3404 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 09:12 | 2022-09-15 09:12 | 2022-09-15 09:11 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2405 | Ethane Refrigerated Tank - Tank Base Slab - Top Reinforcement Plan Part 2 | 1 | EA1 | 7650-8310-44-810-3405 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 09:12 | 2022-09-15 09:12 | 2022-09-15 09:12 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2406 | Ethane Refrigerated Tank - Tank Base Slab - Top Reinforcement Bar Bending Schedule | 1 | EA1 | 7650-8310-44-810-3406 | Deliverable | 2 | IN - 4 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-15 09:12 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2407 | Ethane Refrigerated Tank - Tank Base Slab - Sections and Details Part 1 | 1 | EA1 | 7650-8310-44-810-3407 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-15 09:12 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2408 | Ethane Refrigerated Tank - Tank Base Slab - Sections and Details Part 2 | 1 | EA1 | 7650-8310-44-810-3408 | Deliverable | 2 | IN - 1 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-15 09:12 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/2409 | Ethane Refrigerated Tank - Tank Base Slab - Spacers and Shear Reinforcement | 1 | EA1 | 7650-8310-44-810-3409 | Deliverable | 2 | IN - 4 | 37 | 37 | CG1 |  | AE370000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TD37/DWG/6000/3102 | GENERAL ARRANGEMENT DRAWING - TANK WALL - EMBEDDED PLATES 0-90° (INCL. EAVESBEAM) |  |  | 7650-8310-44-810-3302 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3103 | GENERAL ARRANGEMENT DRAWING - TANK WALL - EMBEDDED PLATES 90-180° (INCL. EAVESBEAM) |  |  | 7650-8310-44-810-3303 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3104 | GENERAL ARRANGEMENT DRAWING - TANK WALL - EMBEDDED PLATES 180-270° (INCL. EAVESBEAM) |  |  | 7650-8310-44-810-3304 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3105 | GENERAL ARRANGEMENT DRAWING - TANK WALL - EMBEDDED PLATES 270-360° (INCL. EAVESBEAM) |  |  | 7650-8310-44-810-3305 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3106 | GENERAL ARRANGEMENT DRAWING - TANK WALL - EMBEDDED PLATES SECTIONS (INCL. EAVESBEAM) |  |  | 7650-8310-44-810-3306 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3201 | PRESTRESSING DRAWING - TANK WALL - HORIZONTAL PRESTRESSING |  |  | 7650-8310-44-810-3307 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3202 | PRESTRESSING DRAWING - TANK WALL - HORIZONTAL BUTTRESS ANCHORAGE AT 45° |  |  | 7650-8310-44-810-3308 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3203 | PRESTRESSING DRAWING - TANK WALL - HORIZONTAL BUTTRESS ANCHORAGE AT 135° |  |  | 7650-8310-44-810-3309 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3204 | PRESTRESSING DRAWING - TANK WALL - HORIZONTAL BUTTRESS ANCHORAGE AT 225° |  |  | 7650-8310-44-810-3310 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3205 | PRESTRESSING DRAWING - TANK WALL - HORIZONTAL BUTTRESS ANCHORAGE AT 315° |  |  | 7650-8310-44-810-3311 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3206 | PRESTRESSING DRAWING - TANK WALL - ELEVATIONS OF HORIZONTAL TENDONS |  |  | 7650-8310-44-810-3312 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3207 | PRESTRESSING DRAWING - TANK WALL - VERTICAL PRESTRESSING BUTTRESS |  |  | 7650-8310-44-810-3313 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3208 | PRESTRESSING DRAWING - TANK WALL - TEMPORARY CONSTRUCTION OPENING SMALL AT 81° |  |  | 7650-8310-44-810-3314 | Deliverable | 2 |  | 37 | 37 | CG1 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3209 | PRESTRESSING DRAWING - TANK WALL - TEMPORARY CONSTRUCTION OPENING LARGE AT 201.6° |  |  | 7650-8310-44-810-3315 | Deliverable | 2 |  | 37 | 37 | CG1 |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3210 | PRESTRESSING DRAWING - TANK WALL - HORIZONTAL SPACERS AND DETAILS |  |  | 7650-8310-44-810-3316 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3211 | PRESTRESSING DRAWING - TANK WALL - VERTICAL SPACERS AND DETAILS |  |  | 7650-8310-44-810-3317 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3301 | REINFORCEMENT DRAWING - TANK WALL - MAIN REINFORCEMENT |  |  | 7650-8310-44-810-3318 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3302 | REINFORCEMENT DRAWING - TANK WALL - SECTIONS AND DETAILS 1 |  |  | 7650-8310-44-810-3319 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3303 | REINFORCEMENT DRAWING - TANK WALL - SECTIONS AND DETAILS 2 |  |  | 7650-8310-44-810-3320 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3304 | REINFORCEMENT DRAWING - TANK WALL - SECTIONS AND DETAILS - WALL RING 1 TO 3 |  |  | 7650-8310-44-810-3321 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3305 | REINFORCEMENT DRAWING - TANK WALL - SECTIONS AND DETAILS - WALL RING 4 TO 7 |  |  | 7650-8310-44-810-3322 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3306 | REINFORCEMENT DRAWING - TANK WALL - ADDITIONAL REINFORCEMENT AT BUTTRESS 45° |  |  | 7650-8310-44-810-3323 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3307 | REINFORCEMENT DRAWING - TANK WALL - ADDITIONAL REINFORCEMENT AT BUTTRESS 135° |  |  | 7650-8310-44-810-3324 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3308 | REINFORCEMENT DRAWING - TANK WALL - ADDITIONAL REINFORCEMENT AT BUTTRESS 225° |  |  | 7650-8310-44-810-3325 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3309 | REINFORCEMENT DRAWING - TANK WALL - ADDITIONAL REINFORCEMENT AT BUTTRESS 315° |  |  | 7650-8310-44-810-3326 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3320 | REINFORCEMENT DRAWING - TANK WALL - PREFABRICATED MATS 1 |  |  | 7650-8310-44-810-3327 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3321 | REINFORCEMENT DRAWING - TANK WALL - PREFABRICATED MATS 2 |  |  | 7650-8310-44-810-3328 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3330 | REINFORCEMENT DRAWING - TANK WALL - COUPLERS AROUND LARGE TCO |  |  | 7650-8310-44-810-3329 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3331 | REINFORCEMENT DRAWING - TANK WALL - COUPLERS AROUND SMALL TCO |  |  | 7650-8310-44-810-3330 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3332 | REINFORCEMENT DRAWING - TANK WALL - CLOSING OF LARGE TCO |  |  | 7650-8310-44-810-3331 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3333 | REINFORCEMENT DRAWING - TANK WALL - CLOSING OF SMALL TCO |  |  | 7650-8310-44-810-3332 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/3341 | REINFORCEMENT BAR BENDING SCHEDULE - TANK WALL |  |  | 7650-8310-44-810-3333 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/DWG/6000/4201 | PRESTRESSING DRAWING - TANK EAVESBEAM - HORIZONTAL PRESTRESSING |  |  | 7650-8310-44-810-3411 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/4202 | PRESTRESSING DRAWING - TANK EAVESBEAM - VERTICAL PRESTRESSING TOP |  |  | 7650-8310-44-810-3412 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/4301 | REINFORCEMENT DRAWING - TANK EAVESBEAM - MAIN REINFORCEMENT |  |  | 7650-8310-44-810-3413 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/4302 | REINFORCEMENT DRAWING - TANK EAVESBEAM - SECTIONS AND DETAILS |  |  | 7650-8310-44-810-3414 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/4303 | REINFORCEMENT DRAWING - TANK EAVESBEAM - ADDITIONAL REINFORCEMENT AT BUTTRESS 45° & 225° |  |  | 7650-8310-44-810-3415 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/4304 | REINFORCEMENT DRAWING - TANK EAVESBEAM - ADDITIONAL REINFORCEMENT AT BUTTRESS 135° & 315° |  |  | 7650-8310-44-810-3416 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/4311 | REINFORCEMENT BAR BENDING SCHEDULE - TANK EAVESBEAM |  |  | 7650-8310-44-810-3417 | Deliverable | 2 |  | 37 | 37 |  |  | AE372664 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5101 | GENERAL ARRANGEMENT DRAWING - TANK DOME ROOF- NOZZLES - PLAN |  |  | 7650-8310-44-810-3501 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5102 | GENERAL ARRANGEMENT DRAWING - TANK DOME ROOF- NOZZLES - PLAN - SECTIONS |  |  | 7650-8310-44-810-3502 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5103 | GENERAL ARRANGEMENT DRAWING - TANK DOME ROOF - PEDESTALS - PLAN |  |  | 7650-8310-44-810-3503 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5301 | REINFORCEMENT DRAWING - TANK DOME ROOF - MAIN BOTTOM REINFORCEMENT 1 |  |  | 7650-8310-44-810-3504 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5302 | REINFORCEMENT DRAWING - TANK DOME ROOF - MAIN BOTTOM REINFORCEMENT 2 |  |  | 7650-8310-44-810-3505 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5303 | REINFORCEMENT DRAWING - TANK DOME ROOF - MAIN TOP REINFORCEMENT 1 |  |  | 7650-8310-44-810-3506 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5304 | REINFORCEMENT DRAWING - TANK DOME ROOF - MAIN TOP REINFORCEMENT 2 |  |  | 7650-8310-44-810-3507 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5305 | REINFORCEMENT DRAWING - TANK DOME ROOF - SECTION AND DETAILS |  |  | 7650-8310-44-810-3508 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5306 | REINFORCEMENT DRAWING - TANK DOME ROOF - SHEAR AND SPACER REINFORCEMENT |  |  | 7650-8310-44-810-3509 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5307 | REINFORCEMENT DRAWING - TANK DOME ROOF - ADDITIONAL BOTTOM REINFORCEMENT |  |  | 7650-8310-44-810-3510 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5308 | REINFORCEMENT DRAWING - TANK DOME ROOF - ADDITIONAL INTERMEDIATE REINFORCEMENT |  |  | 7650-8310-44-810-3511 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5309 | REINFORCEMENT DRAWING - TANK DOME ROOF - ADDITIONAL TOP REINFORCEMENT |  |  | 7650-8310-44-810-3512 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5311 | REINFORCEMENT BAR BENDING SCHEDULE - TANK DOME ROOF 1 |  |  | 7650-8310-44-810-3534 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5312 | REINFORCEMENT BAR BENDING SCHEDULE - TANK DOME ROOF 2 |  |  | 7650-8310-44-810-3535 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5320 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 1 |  |  | 7650-8310-44-810-3513 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5321 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 2 |  |  | 7650-8310-44-810-3514 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5322 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 3 |  |  | 7650-8310-44-810-3515 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5323 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 4 |  |  | 7650-8310-44-810-3516 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5324 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 5 |  |  | 7650-8310-44-810-3517 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5325 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 6 |  |  | 7650-8310-44-810-3518 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5326 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 7 |  |  | 7650-8310-44-810-3519 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5327 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 8 |  |  | 7650-8310-44-810-3520 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5328 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 9 |  |  | 7650-8310-44-810-3521 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5329 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 10 |  |  | 7650-8310-44-810-3522 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5330 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 11 |  |  | 7650-8310-44-810-3523 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5331 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 12 |  |  | 7650-8310-44-810-3524 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5332 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 13 |  |  | 7650-8310-44-810-3525 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5333 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 14 |  |  | 7650-8310-44-810-3526 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5334 | REINFORCEMENT DRAWING - NOZZLES - NOZZLE 15 |  |  | 7650-8310-44-810-3527 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5350 | REINFORCEMENT DRAWING -PEDESTALS - PEDESTAL 1 |  |  | 7650-8310-44-810-3528 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5351 | REINFORCEMENT DRAWING -PEDESTALS - PEDESTAL 2 |  |  | 7650-8310-44-810-3529 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5352 | REINFORCEMENT DRAWING -PEDESTALS - PEDESTAL 3 |  |  | 7650-8310-44-810-3530 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5353 | REINFORCEMENT DRAWING -PEDESTALS - PEDESTAL 4 |  |  | 7650-8310-44-810-3531 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5354 | REINFORCEMENT DRAWING -PEDESTALS - PEDESTAL 5 |  |  | 7650-8310-44-810-3532 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/5355 | REINFORCEMENT DRAWING -PEDESTALS - PEDESTAL 6 |  |  | 7650-8310-44-810-3533 | Deliverable | 2 |  | 37 | 37 |  |  | AE372654 | FALSE |  | 2023-04-02 | 2023-04-02 |  | 2023-04-30 | 2023-04-30
C5663/TD37/DWG/6000/6301 | REINFORCEMENT DRAWING - INNER TANK FOUNDATION | 1 | ES1 | 7650-8310-44-810-3601 | Deliverable | 2 | IN - 1 | 37 | 74 | JH16 |  | AE372654 | FALSE |  | 2023-01-31 | 2023-01-31 | 2022-11-15 | 2023-02-28 | 2023-02-28 | 2022-12-02
C5663/TD37/ITP/1900/2001 | Inspection and Test Plan - Low Temperature Plates | 1 | EA1 | 7650-8430-PR-810-3201 | Deliverable | 2 | IN - 1 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-30
C5663/TD37/ITP/1900/2002 | Inspection and Test Plan - Prefabrication of Low Temperature Plates | 1 | EA1 | 7650-8430-PR-810-3202 | Deliverable | 2 | IN - 1 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-30
C5663/TD37/ITP/1900/2003 | Inspection and Test Plan - Carbon Steel Plates (Mill) | 1 | EA1 | 7650-8430-PR-810-3203 | Deliverable | 2 | IN - 1 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-30
C5663/TD37/ITP/1900/2004 | Inspection and Test Plan - Aluiminium Plate (Mill) | 1 | EA1 | 7650-8430-PR-810-3204 | Deliverable | 2 | IN - 1 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 12:21 | 2022-09-30 | 2022-09-30 | 2022-09-30
C5663/TD37/ITP/1900/2007 | INSPECTION AND TEST PLAN - OUTER LINER / TANK |  |  | 7650-8430-PR-810-3207 | Deliverable | 2 |  | 37 | 37 |  |  | AE374110 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/ITP/1900/2008 | INSPECTION AND TEST PLAN - SUSPENDED DECK |  |  | 7650-8430-PR-810-3208 | Deliverable | 2 |  | 37 | 37 |  |  | AE372724 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/ITP/1900/2009 | INSPECTION AND TEST PLAN - INSULATION |  |  | 7650-8430-PR-810-3209 | Deliverable | 2 |  | 37 | 37 |  |  | AE372724 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/ITP/1900/2010 | INSPECTION AND TEST PLAN - INNER TANK |  |  | 7650-8430-PR-810-3210 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2022-11-02 | 2023-01-27 |  | 2022-11-30 | 2023-02-24
C5663/TD37/ITP/1900/2011 | OUTLINE FABRICATION & ITP - PUMP COLUMN |  |  | 7650-8430-PR-810-3211 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/ITP/1900/2012 | INSPECTION AND TEST PLAN -NOZZLES & INTERNAL PIPING |  |  | 7650-8430-PR-810-3212 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7001 | MATERIAL TAKE-OFF - LOW TEMPERATURE STEEL PLATES |  |  | 7650-8430-BM-810-3701 | Deliverable | 3 |  | 37 | 37 |  |  | AE374130 | FALSE |  | 2022-11-02 | 2023-01-27 |  | 2022-11-30 | 2023-02-24
C5663/TD37/MTO/1900/7002 | MATERIAL TAKE-OFF - CARBON STEEL PLATES |  |  | 7650-8430-BM-810-3702 | Deliverable | 3 |  | 37 | 37 |  |  | AE372734 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7003 | MATERIAL TAKE-OFF - CARBON STEEL PROFILES |  |  | 7650-8430-BM-810-3703 | Deliverable | 3 |  | 37 | 37 |  |  | AE372734 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7004 | MATERIAL TAKE-OFF - STAINLESS STEEL PLATE |  |  | 7650-8430-BM-810-3704 | Deliverable | 3 |  | 37 | 37 |  |  | AE372714 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/MTO/1900/7005 | MATERIAL TAKE-OFF - STAINLESS STEEL SECTIONS |  |  | 7650-8430-BM-810-3705 | Deliverable | 3 |  | 37 | 37 |  |  | AE372714 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/MTO/1900/7006 | MATERIAL TAKE-OFF - ALUMINIUM |  |  | 7650-8430-BM-810-3706 | Deliverable | 3 |  | 37 | 37 |  |  | AE374145 | FALSE |  | 2023-01-03 | 2023-01-03 |  | 2023-01-31 | 2023-01-31
C5663/TD37/MTO/1900/7007 | MATERIAL TAKE-OFF - WELD STUDS |  |  | 7650-8430-BM-810-3707 | Deliverable | 3 |  | 37 | 37 |  |  | AE372734 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/MTO/1900/7008 | MATERIAL TAKE-OFF - STAINLESS NOZZLES & INTERNAL PIPING |  |  | 7650-8430-BM-810-3708 | Deliverable | 3 |  | 37 | 37 |  |  | AE372924 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7009 | MATERIAL TAKE-OFF - CARBON STEEL NOZZLES & INTERNAL PIPING |  |  | 7650-8430-BM-810-3709 | Deliverable | 3 |  | 37 | 37 |  |  | AE372704 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7010 | MATERIAL TAKE-OFF - BOLTS & NUTS |  |  | 7650-8430-BM-810-3710 | Deliverable | 3 |  | 37 | 37 |  |  | AE372704 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7011 | MATERIAL TAKE-OFF - MISCELLANEOUS |  |  | 7650-8430-BM-810-3711 | Deliverable | 3 |  | 37 | 37 |  |  | AE372924 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/1900/7101 | MATERIAL TAKE-OFF - INSULATION MATERIALS |  |  | 7650-8430-BM-810-3721 | Deliverable | 3 |  | 37 | 37 |  |  | AE372724 | FALSE |  | 2023-03-03 | 2023-03-03 |  | 2023-03-31 | 2023-03-31
C5663/TD37/MTO/6000/1001 | Material Take-Off – Concrete for Ethane Refrigerated Tank | A | EO1 | 7650-8310-BM-810-3030 | Deliverable | 3 | IN - 4 | 37 | 37 | JS10 |  | AE372744 | FALSE |  | 2022-09-19 | 2022-09-19 | 2022-09-19 09:29 | 2023-04-30 | 2023-04-30
C5663/TD37/PCD/1900/2020 | OUTLINE PROCEDURE FOR ROOF AIR RAISING |  |  | 7650-8310-PR-810-3020 | Deliverable | 2 |  | 37 | 37 |  |  | AE374108 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/PCD/1900/2021 | OUTLINE TANK HYDROTEST PROCEDURE |  |  | 7650-8310-PR-810-3021 | Deliverable | 2 |  | 37 | 37 |  |  | AE372614 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TD37/RPT/6000/0002 | EVALUATION REPORT OF TEST PILE TESTING RESULTS |  |  | 7650-8310-RP-810-3002 | Deliverable | 2 |  | 37 | 37 |  |  | AE372604 | FALSE |  | 2023-06-02 | 2023-06-02 |  | 2023-06-30 | 2023-06-30
C5663/TD37/TCN/0000/0003 | Seismic Design Basis of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-SP-810-3001 | Deliverable | 2 | IN - 1 | 37 | 111 | DS7 |  | AE370000 | FALSE |  | 2022-07-18 13:55 | 2022-07-18 13:55 | 2022-07-18 13:55 | 2022-08-12 | 2022-08-12 | 2022-08-12
C5663/TD37/TCN/0000/1002 | Outer Containment 3D FEA for Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-CA-810-3003 | Deliverable | 2 | IN - 1 | 37 | 111 | JS10 |  | AE370000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-08-03 17:22 | 2022-09-30 | 2022-09-30 | 2022-09-15 09:13
C5663/TD37/TCN/0000/1005 | Assessment of Soil Data for Ethane Refrigerated Tank Pile Design | 1 | EA1 | 7650-8310-TN-810-3002 | Deliverable | 2 | IN - 1 | 37 | 111 | JS10 |  | AE372674 | FALSE |  | 2022-11-02 | 2022-11-02 | 2022-11-21 | 2022-11-30 | 2022-11-30 | 2022-12-09 19:49
C5663/TD37/TSP/1900/1001 | Overall Design Basis of Ethane Refrigerated Tank | 4 | EA4 | 7650-8430-SP-810-3001 | Deliverable | 2 | IN - 1 | 37 | 111 | JS10 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-25 11:05 | 2022-09-30 | 2022-09-30 | 2022-08-16 14:27
C5663/TD37/TSP/1900/1010 | Technical Specification -Low Temperature Plate | 1 | EA1 | 7650-8430-SP-810-3110 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 12:35 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:04
C5663/TD37/TSP/1900/1011 | TECHNICAL SPECIFICATION - PREFABRICATION SPECIFICATION FOR LOW TEMPERATURE PLATE | 1 | EA1 | 7650-8430-SP-810-3002 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-28 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:04
C5663/TD37/TSP/1900/1012 | Technical Specification - Handling and Storage of Low Temperature Plate | 1 | EA1 | 7650-8430-SP-810-3112 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:04
C5663/TD37/TSP/1900/1013 | Technical Specification - Carbon Steel Plate | 1 | EA1 | 7650-8430-SP-810-3113 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:04
C5663/TD37/TSP/1900/1014 | Technical Specification - Stainless Steel Plates | 1 | EA1 | 7650-8430-SP-810-3114 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 09:43 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:04
C5663/TD37/TSP/1900/1015 | Technical Specification - Stainless Steel Section | 1 | EA1 | 7650-8430-SP-810-3115 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:04
C5663/TD37/TSP/1900/1016 | Technical Specification - Aluminium Plates | 1 | EA1 | 7650-8430-SP-810-3116 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 15:48 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:03
C5663/TD37/TSP/1900/1017 | Technical Specification - Carbon Steel Section | 1 | EA1 | 7650-8430-SP-810-3117 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2022-09-30 | 2022-09-30 | 2022-09-26 14:03
C5663/TD37/TSP/3316/1035 | Technical Specification - Fibreglass Cloth | 1 | EA1 | 7650-8430-SP-810-3135 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 15:58 | 2022-09-30 | 2022-09-30 | 2022-09-26
C5663/TD37/TSP/3316/1036 | Technical Specification - Fibreglass Deck Insulation | 1 | EA1 | 7650-8430-SP-810-3136 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 15:59 | 2022-09-30 | 2022-09-30 | 2022-09-26
C5663/TD37/TSP/3316/1039 | Technical Specification - Miscellaenous Insulation Items | 1 | EA1 | 7650-8430-SP-810-3139 | Deliverable | 2 | IN - 4 | 37 | 37 | SA3 |  | AE370000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 15:59 | 2022-09-30 | 2022-09-30 | 2022-09-26
C5663/TD37/TSP/6000/0001 | Concrete Specification of Ethane Refrigerated Tank | 2 | EA2 | 7650-8310-SP-810-3014 | Deliverable | 2 | IN - 1 | 37 | 37 | JS10 |  | AE370000 | FALSE |  | 2022-07-18 13:53 | 2022-07-18 13:53 | 2022-07-18 13:53 | 2022-08-16 14:27 | 2022-08-16 14:27 | 2022-08-16 14:27
C5663/TD37/TSP/6000/0002 | Technical Specification - Concrete Work of Outer Tank | 1 | EA1 | 7650-8310-SP-810-3002 | Deliverable | 2 | IN - 1 | 37 | 37 | FZ1 |  | AE372664 | FALSE |  | 2022-11-20 | 2022-11-20 | 2022-11-11 18:14 | 2022-12-18 | 2022-12-18 | 2022-11-30 14:43
C5663/TD37/TSP/6000/0003 | TECHNICAL SPECIFICATION - TOLERANCES |  |  | 7650-8310-SP-810-3003 | Deliverable | 2 |  | 37 | 37 | DS7 |  | AE372664 | FALSE |  | 2022-11-20 | 2023-01-10 |  | 2022-12-18 | 2023-01-27
C5663/TD37/TSP/6000/0007 | Technical Specification - Roof Pouring | 1 | EA1 | 7650-8310-SP-810-3007 | Deliverable | 2 | IN - 1 | 37 | 37 | DS7 |  | AE372654 | FALSE |  | 2023-03-31 | 2023-03-31 | 2022-12-01 17:33 | 2023-04-28 | 2023-04-28 | 2023-01-11 15:25
C5663/TD37/TSP/6000/0009 | TECHNICAL SPECIFICATION - TEST PILES | 1 | EA1 | 7650-8310-SP-810-3009 | Deliverable | 2 | IN - 1 | 37 | 37 | DS7 |  | AE372674 | FALSE |  | 2023-11-23 | 2023-11-23 | 2022-11-28 19:11 | 2022-12-21 | 2023-01-27 | 2023-01-11 15:25
C5663/TD37/TSP/6000/0010 | Technical Specification - Settlement Monitoring | 1 | EF1 | 7650-8310-SP-810-3010 | Deliverable | 2 | IN - 1 | 37 | 37 | DS7 |  | AE372664 | FALSE |  | 2023-01-31 | 2023-01-31 | 2022-11-23 12:39 | 2023-02-28 | 2023-02-28 | 2022-12-14 13:09
C5663/TD37/TSP/6000/1001 | Post-Tensioning System Specification of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-SP-810-3015 | Deliverable | 2 | IN - 1 | 37 | 37 | JS10 |  | AE370000 | FALSE |  | 2022-07-18 13:45 | 2022-07-18 13:45 | 2022-07-18 13:45 | 2022-09-05 | 2022-09-05 | 2022-08-29 16:33
C5663/TH21/LST/0000/0002 | Master Document Register for Ethane Refrigerated Tank | 2 | EA2 | 7650-8820-IN-810-3003 | Deliverable |  |  | 21 | 80 | AM4 |  | AE211000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-10-27 11:11 | 2023-12-20 | 2023-12-20 | 2022-11-28 14:07
C5663/TH21/LST/0000/0006 | Project Risk Register of Ethane Refrigerated Tank | A | EO1 | 7650-8820-RA-810-3006 | Deliverable | 2 | IN - 2 | 21 | 40 | MD13 |  | AE211000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-08 | 2023-12-20 | 2023-12-20
C5663/TH21/LST/0000/3003 | Interface Register for Ethane Refrigerated Tank | 1 | EA1 | 7650-8820-IF-810-3003 | Deliverable | 2 | IN - 2 | 21 | 40 | AM4 |  | AE211000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-22 11:11 | 2022-09-30 | 2022-09-30 | 2022-10-27 08:49
C5663/TH21/LST/4100/0001 | Spare Parts List for Ethane Refrigerated Storage System |  |  | 7650-8820-IN-810-3004 | Deliverable | 2 |  | 21 | 80 |  |  | AE211000 | FALSE |  | 2023-06-30 | 2023-06-30 |  | 2023-12-20 | 2023-12-20
C5663/TH21/PCD/0000/3007 | Guideline 3D Model Design Review | 1 | EF1 | 7650-8820-PR-810-3007 | Deliverable | 2 | IN - 1 | 21 | 38 | AM4 |  | AE210000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-20 16:58 | 2022-09-30 | 2022-09-30 | 2022-10-14 11:01
C5663/TH21/PCD/0000/3014 | S3D Implementation Procedure | 2 | EF1 | 7650-8820-PR-810-3014 | Deliverable | 2 |  | 21 | 16 | JM10 |  | AE211000 | FALSE |  | 2022-09-21 | 2022-09-21 | 2022-09-21 11:30 | 2022-12-21 | 2022-12-21 | 2022-12-22
C5663/TH21/PCD/0000/3015 | SPID Implementation Procedure | 1 | EA1 | 7650-8820-PR-810-3015 | Deliverable | 2 |  | 21 | 16 | JM10 |  | AE211000 | FALSE |  | 2022-09-21 | 2022-09-21 | 2022-09-21 11:31 | 2022-12-21 | 2023-01-27 | 2023-01-27 13:01
C5663/TH21/PCD/0000/3016 | SPI Implementation Procedure | B | EO2 | 7650-8820-PR-810-3016 | Deliverable | 2 |  | 21 | 16 | JM10 |  | AE211000 | FALSE |  | 2022-09-20 | 2022-09-20 | 2022-09-20 15:35 | 2022-12-21 | 2023-01-27
C5663/TH21/PCD/0000/3017 | SEL Implementation Procedure | B | EO2 | 7650-8820-PR-810-3017 | Deliverable | 2 |  | 21 | 16 | JM10 |  | AE211000 | FALSE |  | 2022-09-26 | 2022-09-26 | 2022-09-26 14:32 | 2022-12-21 | 2023-01-27
C5663/TH21/RPT/0080/0001 | 30% 3D Review Report for Ethane Refrigerated Tank | 1 | EA1 | 7650-8820-RP-810-3001 | Deliverable | 2 | IN - 1 | 21 | 24 | AM4 |  | AE322884 | FALSE |  | 2022-11-04 | 2022-11-04 | 2022-10-28 16:29 | 2022-12-21 | 2022-12-21 | 2022-12-20 17:08
C5663/TH21/RPT/0080/0002 | 60% 3D Review Report for Ethane Refrigerated Tank |  |  | 7650-8820-RP-810-3002 | Deliverable | 2 |  | 21 | 40 |  |  | AE322884 | FALSE |  | 2023-05-12 | 2023-05-12 |  | 2023-07-31 | 2023-07-31
C5663/TH21/RPT/0080/0003 | 90% 3D Review Report for Ethane Refrigerated Tank |  |  | 7650-8820-RP-810-3003 | Deliverable | 2 |  | 21 | 24 |  |  | AE322884 | FALSE |  | 2023-10-20 | 2023-10-20 |  | 2023-11-24 | 2023-11-24
C5663/TH21/RPT/0080/0004 | Plot Plan Review Report for Ethane Refrigerated Tank | 1 | EF1 | 7650-8820-RP-810-3004 | Deliverable | 2 | IN - 1 | 21 | 8 | AM4 |  | AE322884 | FALSE |  | 2022-11-04 | 2022-11-04 | 2022-11-03 09:56 | 2022-12-21 | 2022-12-21 | 2022-11-14 13:50
C5663/TH21/STD/0000/0001 | Applicable Codes and Standards for Ethane Refrigerated Tank | 1 | EF1 | 7650-8820-IN-810-3001 | Deliverable | 1 | IN - 1 | 21 | 16 | AM4 |  | AE211000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-07 10:40 | 2022-12-21 | 2022-12-21 | 2022-11-28 09:03
C5663/TH21/TCN/0000/0001 | Project Design Basis for Ethane Refrigerated Tank | 2 | EF1 | 7650-8820-TN-810-3001 | Deliverable | 1 | IN - 1 | 21 | 16 | AM4 |  | AE210000 | FALSE |  | 2022-07-20 15:54 | 2022-07-20 15:54 | 2022-07-20 15:54 | 2022-09-30 | 2022-09-30 | 2022-09-22 09:56
C5663/TH31/TCN/0000/0001 | Surface Water Drainage Summary of Ethane Refrigerated Tank | 1 | EA1 | 7650-8310-TN-810-3004 | Deliverable | 2 | IN - 1 | 31 | 8 | FP |  | AE310000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-19 09:26 | 2022-09-30 | 2022-09-30 | 2022-10-14 16:25
C5663/TH32/ADW/0000/1001 | Plot Plan of Ethane Refrigerated Tank | 2 | ES1 | 7650-8230-01-810-3001 | Deliverable | 1 | IN - 2 | 32 | 24 | SS16 |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-27
C5663/TH32/DSH/3510/0001 | Datasheets Tank Vacuum Breakers Valves for Ethane Refrigerated Tank | 1 | EA1 | 7650-8230-DS-810-3008 | Deliverable | 2 | IN - 1 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 20:30 | 2022-09-30 | 2022-09-30 | 2022-09-28 16:25
C5663/TH32/DSH/3516/0001 | Datasheets Tank Pressure Safety Valves for Ethane Refrigerated Tank | 2 | EA2 | 7650-8230-DS-810-3006 | Deliverable | 2 | IN - 1 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 20:30 | 2022-09-30 | 2022-09-30 | 2022-09-28 16:25
C5663/TH32/DSH/3516/0002 | Datasheets Thermal Safety Valves for Ethane Refrigerated Tank | 1 | EA1 | 7650-8230-DS-810-3007 | Deliverable | 2 | IN - 1 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 20:30 | 2022-09-30 | 2022-09-30 | 2022-09-28 16:25
C5663/TH32/DSH/3542/0001 | Datasheets for Interlock System |  |  | 7650-8230-DS-810-3010 | Deliverable | 3 |  | 32 | 10 | AK13 |  | AE323000 | FALSE |  | 2023-01-31 | 2022-12-31 |  | 2023-02-28 | 2023-02-28
C5663/TH32/DSH/3551/0001 | Datasheets Manual Ball Valves for Ethane Refrigerated Tank | 2 | EA2 | 7650-8230-DS-810-3009 | Deliverable | 3 |  | 32 | 10 | AC4 |  | AE321000 | FALSE |  | 2022-10-31 | 2022-10-31 | 2022-10-24 15:01 | 2022-11-30 | 2022-11-30 | 2022-11-03 09:27
C5663/TH32/DSH/3552/0001 | Datasheets Actuated Gate Valves for Ethane Refrigerated Tank | 2 | EA2 | 7650-8230-DS-810-3004 | Deliverable | 3 | IN - 2 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-23 | 2022-09-30 | 2022-09-30 | 2022-09-28 16:26
C5663/TH32/DSH/3553/0001 | Datasheets Manual Gate, Globe and Check Valves for Ethane Refrigerated Tank | 2 | EA2 | 7650-8230-DS-810-3003 | Deliverable | 3 | IN - 1 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-23 | 2022-09-30 | 2022-09-30 | 2022-10-14 09:15
C5663/TH32/DSH/3556/0001 | Datasheets Manual Butterfly Valves for Ethane Refrigerated Tank | 2 | EA2 | 7650-8230-DS-810-3001 | Deliverable | 3 | IN - 1 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-19 | 2022-09-30 | 2022-09-30 | 2022-10-11
C5663/TH32/DSH/3556/0002 | Datasheets Actuated Butterfly Valves for Ethane Refrigerated Tank | 2 | EA2 | 7650-8230-DS-810-3002 | Deliverable | 3 | IN - 2 | 32 | 10 | AG8 |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-23 | 2022-09-30 | 2022-09-30 | 2022-09-28 16:26
C5663/TH32/DSH/3557/0001 | Datasheets for Strainers | A | EO1 | 7650-8230-DS-810-3011 | Deliverable | 3 |  | 32 | 10 | AK13 |  | AE323000 | FALSE |  | 2023-01-31 | 2023-01-31 | 2023-01-09 20:58 | 2023-02-28 | 2023-02-28
C5663/TH32/LST/3500/0001 | Valve List | A | EO1 | 7650-8230-IN-810-3501 | Deliverable | 3 |  | 32 | 10 | LQ1 |  | AE321000 | FALSE |  | 2022-10-31 | 2022-12-23 | 2023-01-09 20:58 | 2022-11-30 | 2023-01-31
C5663/TH32/LST/3500/0002 | Special Piping Item List |  |  | 7650-8230-IN-810-3502 | Deliverable | 3 |  | 32 | 10 | ATH |  | AE323000 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TH32/PCD/0000/0001 | Pipe Stress analysis Procedure | 2 | EA2 | 7650-8230-SP-810-3003 | Deliverable | 2 | IN - 2 | 32 | 24 | IJ2 |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-15 16:28 | 2022-09-30 | 2022-09-30 | 2022-09-30 12:45
C5663/TH32/PCD/0000/0002 | Guideline 3D Model Design | 2 | EF1 | 7650-8820-PR-810-3001 | Deliverable | 1 | IN - 1 | 32 | 32 | ATH |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-20 16:58 | 2022-09-30 | 2022-09-30 | 2022-10-27 12:00
C5663/TH32/TAD/3700/0001 | Piping & Instrument Assembly Drawings | 1 | EA1 | 7650-8230-54-810-3001 | Deliverable | 2 |  | 32 | 6 | SS16 |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-20 16:58 | 2022-09-30 | 2023-01-27 | 2023-01-17 14:42
C5663/TH32/TSP/0000/0001 | Specification of Piping Materials for Ethane Refrigerated Tank | 1 | EA1 | 7650-8230-SP-810-3002 | Deliverable | 2 | IN - 1 | 32 | 40 | ATH |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-19 15:23 | 2022-09-30 | 2022-09-30 | 2022-10-27 08:45
C5663/TH32/TSP/0000/0002 | Specification of Piping Supports for Ethane Refrigerated Tank | 1 | EA1 | 7650-8230-SP-810-3004 | Deliverable | 2 | IN - 1 | 32 | 6 | PS7 |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-19 | 2022-09-30 | 2022-09-30 | 2022-09-30 14:09
C5663/TH32/TSP/0000/0003 | Specification of Piping Insulation for Ethane Refrigerated Tank | 1 | EF1 | 7650-8230-SP-810-3008 | Deliverable | 2 | IN - 1 | 32 | 6 | ATH |  | AE321000 | FALSE |  | 2022-10-31 | 2022-10-31 | 2022-11-08 15:14 | 2022-11-30 | 2022-11-30 | 2022-12-15 16:21
C5663/TH32/TSP/0000/0004 | Painting Specification for Ethane Refrigerated Tank | 1 | EF1 | 7650-8440-SP-810-3016 | Deliverable | 2 | IN - 1 | 32 | 6 | ATH |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-10-27 08:46 | 2022-09-30 | 2022-09-23 | 2022-12-15 16:21
C5663/TH32/TSP/3500/0001 | Technical Specification for the supply of valves | 1 | EA1 | 7650-8230-SP-810-3501 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE321000 | FALSE |  | 2022-10-31 | 2022-10-31 | 2022-11-02 | 2022-11-30 | 2022-11-30 | 2022-11-16 17:25
C5663/TH32/TSP/3510/0001 | Technical Specification – Safety Valves for Ethane Refrigerated Tank | A | EO1 | 7650-8230-SP-810-3511 | Deliverable | 2 |  | 32 | 6 | LQ1 |  | AE321000 | FALSE |  | 2022-10-31 | 2022-10-31 | 2022-12-22 14:25 | 2022-11-30 | 2023-01-27
C5663/TH32/TSP/3542/0001 | Specification of Interlock System |  |  | 7650-8230-SP-810-3020 | Deliverable | 2 |  | 32 | 6 | AK13 |  | AE323000 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TH32/TSP/3557/0001 | Specification of Strainers | A | EO1 | 7650-8230-SP-810-3557 | Deliverable | 2 |  | 32 | 6 | AK13 |  | AE323000 | FALSE |  | 2023-01-31 | 2023-01-31 | 2023-01-09 20:59 | 2023-02-28 | 2023-02-28
C5663/TH32/TSP/3700/0001 | Technical Specification - Spectacle Blind, Spade and Spacer | 1 | EA1 | 7650-8230-SP-810-3005 | Deliverable | 2 | IN - 1 | 32 | 6 | ATH |  | AE320000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-23 13:55 | 2022-09-30 | 2022-09-30 | 2022-10-21
C5663/TH32/TSP/3703/0001 | Technical Specification - Stainless Steel Pipes | 1 | EA1 | 7650-8230-SP-810-3021 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 15:54 | 2022-07-31 15:54 | 2022-07-20 15:54 | 2022-09-30 | 2022-09-30 | 2022-09-23 13:06
C5663/TH32/TSP/3703/0002 | Technical Specification - Stainless Steel Fittings | 1 | EA1 | 7650-8230-SP-810-3022 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 15:30 | 2022-07-31 15:30 | 2022-07-25 15:30 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:31
C5663/TH32/TSP/3703/0003 | Technical Specification - Stainless Steel Flanges | 1 | EA1 | 7650-8230-SP-810-3023 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 18:52 | 2022-07-31 18:52 | 2022-07-25 18:52 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:31
C5663/TH32/TSP/3703/0004 | Specification of Utility Hose Couplings |  |  | 7650-8230-SP-810-3030 | Deliverable | 2 |  | 32 | 6 | ATH |  | AE323000 | FALSE |  | 2023-01-31 | 2023-01-31 |  | 2023-02-28 | 2023-02-28
C5663/TH32/TSP/3703/0005 | Technical Specification - Carbon Steel Pipes | 1 | EA1 | 7650-8230-SP-810-3024 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 19:22 | 2022-07-31 19:22 | 2022-07-27 19:22 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:31
C5663/TH32/TSP/3703/0006 | Technical Specification - Carbon Steel Fittings | 1 | EA1 | 7650-8230-SP-810-3025 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 19:21 | 2022-07-31 19:21 | 2022-07-27 19:21 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:31
C5663/TH32/TSP/3703/0007 | Technical Specification - Carbon Steel Flanges | 1 | EA1 | 7650-8230-SP-810-3026 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 19:20 | 2022-07-31 19:20 | 2022-07-27 19:20 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:31
C5663/TH32/TSP/3703/0008 | INEOS Particular Material Appraisal | 1 | EF1 | 7650-8230-DS-810-3005 | Deliverable | 2 | IN - 1 | 32 | 24 | ATH |  | AE320000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-26 | 2022-09-30 | 2022-09-30 | 2022-11-08 15:13
C5663/TH32/TSP/3705/0001 | Technical Specification - Stainless Steel Bolts and Nuts | 1 | EA1 | 7650-8230-SP-810-3027 | Deliverable | 2 | IN - 1 | 32 | 8 | LQ1 |  | AE320000 | FALSE |  | 2022-07-26 19:02 | 2022-07-26 19:02 | 2022-07-26 19:02 | 2022-09-15 | 2022-09-15 | 2022-09-21 21:31
C5663/TH32/TSP/3705/0002 | Technical Specification - Carbon Steel Bolts and Nuts | 1 | EA1 | 7650-8230-SP-810-3028 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 19:02 | 2022-07-31 19:02 | 2022-07-26 19:02 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:31
C5663/TH32/TSP/3708/0001 | Technical Specification - Spiral Wound Gaskets | 1 | EA1 | 7650-8230-SP-810-3029 | Deliverable | 2 | IN - 1 | 32 | 6 | LQ1 |  | AE320000 | FALSE |  | 2022-07-31 19:02 | 2022-07-31 19:02 | 2022-07-26 19:02 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:32
C5663/TH33/BLD/3000/1001 | Electrical System Block Diagram of Ethane Refrigerated Tank | 1 | EA1 | 7650-8530-75-810-3006 | Deliverable | 2 | IN - 2 | 33 | 41 | WEY |  | AE330000 | FALSE |  | 2022-07-31 19:45 | 2022-07-31 19:45 | 2022-07-28 19:45 | 2022-09-30 | 2022-09-30 | 2022-09-23 13:16
C5663/TH33/CAL/3000/0001 | Cable Sizing Calculation of Ethane Refrigerated Tank | A | EO1 | 7650-8530-CA-810-3007 | Deliverable | 2 | IN - 2 | 33 | 40 | TK9 |  | AE333000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-26 | 2023-05-31 | 2023-05-31
C5663/TH33/CAL/3000/0002 | Network Calculation - Detail Calculation Main Equipment |  |  | 7650-8530-CA-810-3008 | Deliverable | 2 |  | 33 | 40 |  |  | AE333000 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-05-31 | 2023-05-31
C5663/TH33/CAL/3052/0001 | Lighting System Outside - Lighting Fixtures - Basic Calculation | 1 | EA1 | 7650-8530-CA-810-3001 | Deliverable | 2 | IN - 4 | 33 | 21 | TK9 |  | AE332000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-07-27 | 2022-12-21 | 2023-01-27 | 2023-01-16 14:21
C5663/TH33/CAL/3056/0001 | Earthing and Lightning Protection System - Risk assessment/Management analysis | 1 | EA1 | 7650-8530-CA-810-3002 | Deliverable | 2 | IN - 4 | 33 | 21 | KK5 |  | AE330000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-09-26 14:58 | 2022-10-31 | 2022-10-31 | 2022-11-18 10:17
C5663/TH33/CAL/3056/0002 | Earthing and Lightning Protection System - Basic analysis | 1 | EA1 | 7650-8530-CA-810-3003 | Deliverable | 2 | IN - 4 | 33 | 21 | KK5 |  | AE330000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-09-26 14:58 | 2022-10-31 | 2022-10-31 | 2022-11-18 10:17
C5663/TH33/DSH/3033/0001 | LV Power and Control Cables | 1 | EA1 | 7650-8530-DS-810-3006 | Deliverable | 3 | IN - 2 | 33 | 10 | TK9 |  | AE333000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-27 | 2023-05-31 | 2023-05-31 | 2022-09-26 14:59
C5663/TH33/DSH/3038/0001 | Motor Local Control Unit (LCU) - Technical Data | A | EO1 | 7650-8530-DS-810-3001 | Deliverable | 3 | IN - 2 | 33 | 10 | TK9 |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-25 | 2023-03-31 | 2023-03-31
C5663/TH33/DSH/3038/0002 | Motor Safety Switch - Technical Data | A | EO1 | 7650-8530-DS-810-3002 | Deliverable | 3 | IN - 2 | 33 | 10 | TK9 |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-25 | 2023-03-31 | 2023-03-31
C5663/TH33/DSH/3052/0001 | Lighting System Outside - Lighting Fixtures - Technical Data | 1 | EA1 | 7650-8530-DS-810-3003 | Deliverable | 3 | IN - 1 | 33 | 10 | TK9 |  | AE332000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-07-25 | 2022-12-21 | 2023-01-27 | 2023-01-10 14:52
C5663/TH33/DSH/3052/0002 | Lighting System Outside - Junction Boxes - Technical Data | 1 | EA1 | 7650-8530-DS-810-3004 | Deliverable | 3 | IN - 1 | 33 | 10 | TK9 |  | AE332000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-26 | 2022-12-21 | 2023-01-27 | 2023-01-10 14:53
C5663/TH33/DSH/3052/0003 | Lighting System Outside - Lighting Poles Fix Type - Technical Data | A | EO1 | 7650-8530-DS-810-3008 | Deliverable | 3 | IN - 1 | 33 | 10 | TK9 |  | AE332000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-25 | 2022-12-21 | 2023-01-27
C5663/TH33/DSH/3053/0001 | Sockets Outside - Technical Data | 1 | EA1 | 7650-8530-DS-810-3007 | Deliverable | 3 | IN - 1 | 33 | 10 | KK5 |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-23 12:39 | 2022-12-21 | 2022-12-21 | 2022-12-19 13:40
C5663/TH33/DSH/3061/0001 | Cable Routing Materials Outside - Technical Data | 1 | EA1 | 7650-8530-DS-810-3005 | Deliverable | 3 | IN - 1 | 33 | 10 | TK9 |  | AE333000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-25 | 2023-05-31 | 2023-05-31 | 2022-09-20 15:38
C5663/TH33/LOD/3000/0002 | Location of Electrical Equipment - Main Layout | 1 | EA1 | 7650-8530-79-810-3001 | Deliverable | 2 | IN - 2 | 33 | 42 | KK5 |  | AE330000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-21 | 2022-09-30 | 2022-09-30 | 2022-09-30 15:49
C5663/TH33/LOD/3000/1001 | Lighting, Sockets and Local Power Supply Equipment Layout of Ethane Refrigerated Tank | 1 | EA1 | 7650-8530-79-810-3014 | Deliverable | 2 | IN - 1 | 33 | 42 | WEY |  | AE330000 | FALSE |  | 2022-09-10 17:14 | 2022-09-10 17:14 | 2022-07-28 17:14 | 2022-09-30 | 2022-12-23 | 2022-12-12
C5663/TH33/LOD/3056/0001 | Earthing System – Detailed Foundation Earth Layout for Tank Part 01 | 2 | EA1 | 7650-8530-72-810-3311 | Deliverable | 1 | IN - 4 | 33 | 42 | WEY |  | AE330000 | FALSE |  | 2022-08-31 16:29 | 2022-08-31 16:29 | 2022-07-28 16:29 | 2022-10-31 | 2022-10-31 | 2022-09-01
C5663/TH33/LOD/3056/0002 | Earthing System – Detailed Foundation Earth Layout for Tank Part 02 | 2 | EA1 | 7650-8530-72-810-3312 | Deliverable | 1 | IN - 4 | 33 | 42 | WEY |  | AE330000 | FALSE |  | 2022-08-31 16:28 | 2022-08-31 16:28 | 2022-07-28 16:28 | 2022-10-31 | 2022-10-31 | 2022-09-01
C5663/TH33/LOD/3056/0003 | Earthing System – Detailed Foundation Earth Layout for Tank Part 03 - Inside Slab and Wall - Details | 2 | EA1 | 7650-8530-72-810-3401 | Deliverable | 1 | IN - 4 | 33 | 42 | WEY |  | AE330000 | FALSE |  | 2022-07-28 16:28 | 2022-07-28 16:28 | 2022-07-28 16:28 | 2022-10-31 | 2022-10-31 | 2022-09-01
C5663/TH33/LOD/3056/0004 | Earthing System – Detailed Foundation Earth Layout for Tank Part 04 - Inside Slab and Wall - Details II Embeddments for Tank Riser | 2 | EA1 | 7650-8530-72-810-3402 | Deliverable | 1 | IN - 4 | 33 | 42 | WEY |  | AE330000 | FALSE |  | 2022-07-28 | 2022-07-28 | 2022-07-28 | 2022-10-31 | 2022-10-31 | 2022-09-01
C5663/TH33/LOD/3056/0005 | Earthing System - Detailed Foundation Earth Layout for Tank Part 05 - xx |  |  | 7650-8530-72-810-3511 | Deliverable |  |  | 33 | 10 |  |  | AE334000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/TH33/LOD/3056/0006 | Earthing System - Detiled Foundtion Earth Layout for Tank Part 06 - xx |  |  | 7650-8530-72-810-3512 | Deliverable | 1 |  | 33 | 10 |  |  | AE334000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/TH33/LOD/3056/3501 | Earthing System - Detailed Foundation Earth Layout for Stairway & Escape Ladder | A | EO1 | 7650-8530-72-810-3501 | Deliverable | 1 |  | 33 | 42 | WEY |  | AE330000 | FALSE |  | 2022-09-30 | 2022-12-23 | 2023-01-24 | 2022-10-31 | 2023-01-30
C5663/TH33/LOD/3056/3701 | Earthing System - Detailed Foundation Earth Layoutfor Stair Tower |  |  | 7650-8530-72-810-3701 | Deliverable | 1 |  | 33 | 10 |  |  | AE335000 | FALSE |  | 2023-11-30 | 2023-11-30 |  | 2023-12-20 | 2023-12-20
C5663/TH33/LOD/3061/1002 | Electrical Cable Tray Layout Of Ethane Refrigerated Tank - 10 - Ethane Storage Area | 1 | EA1 | 7650-8530-78-810-3012 | Deliverable | 2 | IN - 1 | 33 | 8 | WEY |  | AE330000 | FALSE |  | 2022-07-28 16:29 | 2022-07-28 16:29 | 2022-07-28 16:29 | 2022-09-15 | 2022-09-15 | 2022-09-26
C5663/TH33/LST/3000/0001 | Electrical Load List of Ethane Refrigerated Tank | 1 | EA1 | 7650-8530-SH-810-3008 | Deliverable | 2 | IN - 1 | 33 | 70 | TK9 |  | AE330000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-27 19:21 | 2022-09-30 | 2022-09-30 | 2022-09-19 14:20
C5663/TH33/LST/3030/0001 | Electrical Cable List of Ethane Refrigerated Tank | 1 | EA1 | 7650-8530-73-810-3010 | Deliverable | 2 | IN - 2 | 33 | 70 | TK9 |  | AE330000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-07-27 | 2022-09-30 | 2022-09-30 | 2022-09-22
C5663/TH33/RPT/3056/0001 | Earthing and Lightning Protection System - Measuring Report of Soil Resistivity | A | EO1 | 7650-8530-RP-810-3001 | Deliverable | 2 | IN - 4 | 33 | 8 | TK9 |  | AE330000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 11:44 | 2022-10-31 | 2023-03-31
C5663/TH33/RPT/3056/0002 | Earthing and Lightning Protection System - Stroke Density Report | 1 | EA1 | 7650-8530-RP-810-3002 | Deliverable | 2 | IN - 1 | 33 | 8 | TK9 |  | AE330000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 16:28 | 2022-10-31 | 2022-10-31 | 2022-09-23 13:17
C5663/TH33/SLD/3000/0001 | General Single Line Diagram | A | EO1 | 7650-8530-70-810-3012 | Deliverable | 2 | IN - 2 | 33 | 30 | WEY |  | AE333000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 19:45 | 2023-05-31 | 2023-05-31
C5663/TH33/TAD/3038/0001 | Motor Local Control Unit (LCU) – Typical for Fabrication | 1 | EA1 | 7650-8530-77-810-3014 | Deliverable | 2 | IN - 1 | 33 | 15 | WEY |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 | 2023-03-31 | 2023-03-31 | 2022-10-07
C5663/TH33/TAD/3038/0002 | Motor Local Control Unit (LCU) – Typical Installation Details | A | EO1 | 7650-8530-77-810-3015 | Deliverable | 2 | IN - 2 | 33 | 15 | WEY |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 | 2023-03-31 | 2023-03-31
C5663/TH33/TAD/3038/0003 | Motor Safety Switch – Typical for Fabrication | A | EO1 | 7650-8530-77-810-3016 | Deliverable | 2 | IN - 2 | 33 | 15 | WEY |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 | 2023-03-31 | 2023-03-31
C5663/TH33/TAD/3038/0004 | Motor Safety Switch – Typical Installation Details | A | EO1 | 7650-8530-77-810-3017 | Deliverable | 2 | IN - 2 | 33 | 15 | WEY |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 | 2023-03-31 | 2023-03-31
C5663/TH33/TAD/3052/0001 | Lighting System Outside – Lighting Fixtures - Typical for Fabrication | A | EO1 | 7650-8530-77-810-3018 | Deliverable | 2 | IN - 2 | 33 | 15 | WEY |  | AE332000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 16:29 | 2022-12-21 | 2023-01-27
C5663/TH33/TAD/3052/0002 | Lighting System Outside – Lighting Fixtures - Typical Installation Details | 1 | EA1 | 7650-8530-77-810-3019 | Deliverable | 2 | IN - 1 | 33 | 15 | WEY |  | AE332000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 16:29 | 2022-12-21 | 2023-01-27 | 2023-01-13 17:56
C5663/TH33/TAD/3053/0001 | Socket Units Outdoor (NDU) - Typical for Fabrication - Power Sockets 400V AC Ex-Proof | 1 | EA1 | 7650-8530-77-810-3020 | Deliverable | 2 | IN - 1 | 33 | 15 | KK5 |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-24 | 2022-12-21 | 2023-01-27 | 2023-01-12 10:38
C5663/TH33/TAD/3053/0002 | Socket Units Outdoor (NDU) - Typical Installation Details | 1 | EA1 | 7650-8530-77-810-3021 | Deliverable | 2 | IN - 1 | 33 | 15 | KK5 |  | AE332000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-24 | 2022-12-21 | 2023-01-27 | 2023-01-18 10:14
C5663/TH33/TAD/3056/0001 | TAD of Ethane Refrigerated - Tank Earthing & Lightning Protection System | 1 | EA1 | 7650-8530-72-810-3004 | Deliverable | 2 | IN - 4 | 33 | 15 | WEY |  | AE330000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 11:42 | 2022-09-30 | 2022-09-30 | 2022-09-27
C5663/TH33/TAD/3061/0001 | Cable Routing above Ground – Typical Installation Design | 1 | EA1 | 7650-8530-77-810-3013 | Deliverable | 2 | IN - 4 | 33 | 15 | WEY |  | AE333000 | FALSE |  | 2022-07-31 11:44 | 2022-07-31 11:44 | 2022-07-28 11:44 | 2023-05-31 | 2023-05-31 | 2022-09-13
C5663/TH33/TCN/3000/0001 | General Description of Electrical System for Ethane Refrigerated Tank | 2 | EA2 | 7650-8530-TN-810-3001 | Deliverable | 1 | IN - 3 | 33 | 10 | KK5 |  | AE330000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-15 | 2022-09-30 | 2022-09-30 | 2022-08-31
C5663/TH33/TCN/3056/0001 | Ethane Refrigerated Tank Earthing & Lightning Protection System Specification | 1 | EA1 | 7650-8530-SP-810-3002 | Deliverable | 1 | IN - 1 | 33 | 10 | TK9 |  | AE330000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-27 19:20 | 2022-09-30 | 2022-09-30 | 2022-09-19 14:20
C5663/TH33/TSP/0000/0001 | Electrical Erection Works | B | EO2 | 7650-8530-SP-810-3003 | Deliverable | 1 | IN - 4 | 33 | 10 | TK9 |  | AE331000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-25 | 2023-03-31 | 2023-03-31
C5663/TH33/TSP/3061/0001 | Cable Routing Materials Outside - For Above Ground Installation | A | EO1 | 7650-8530-SP-810-3005 | Deliverable | 1 | IN - 3 | 33 | 10 | TK9 |  | AE333000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-25 | 2023-05-31 | 2023-05-31
C5663/TH34/BLD/3200/1001 | Block Diagram of Instrumentation System for Ethane Refrigerated Tank | 1 | EA1 | 7650-8550-64-810-3008 | Deliverable | 2 | IN - 1 | 34 | 30 | JM10 |  | AE340000 | FALSE |  | 2022-07-31 | 2022-07-31 |  | 2022-09-30 | 2022-09-30 | 2022-07-25 15:30
C5663/TH34/BLD/3219/1001 | Block Diagram of Tank Gauging System for Ethane Refrigerated Tank | 2 | EA2 | 7650-8550-64-810-3007 | Deliverable | 2 | IN - 1 | 34 | 20 | JM10 |  | AE340000 | FALSE |  | 2022-07-31 | 2022-07-31 |  | 2022-09-30 | 2022-09-30 | 2022-07-26
C5663/TH34/DGR/3201/0001 | Instrument Loop Diagrams for Ethane Refrigerated Tank |  |  | 7650-8550-69-810-3001 | Deliverable | 3 |  | 34 | 80 |  |  | AE344000 | FALSE |  | 2023-04-28 | 2023-04-28 |  | 2023-06-30 | 2023-06-30
C5663/TH34/DGR/3261/3001 | Junction Box Termination Diagram for Ethane Refrigerated Tank | A | EO1 | 7650-8550-66-810-3001 | Deliverable | 3 | IN - 3 | 34 | 60 | JM10 |  | AE344000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-09-27 16:45 | 2023-06-30 | 2023-06-30
C5663/TH34/DSH/2701/0001 | Instrument Datasheet - Gas Detection | B | EO2 | 7650-8550-DS-810-3001 | Deliverable | 3 | IN - 2 | 34 | 40 | JM10 |  | AE342000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/2701/0002 | Instrument Datasheet - Flame Detection | B | EO2 | 7650-8550-DS-810-3002 | Deliverable | 3 | IN - 2 | 34 | 40 | JM10 |  | AE342000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/2701/0003 | Instrument Datasheet - Alarm Devices |  |  | 7650-8550-DS-810-3004 | Deliverable | 3 |  | 34 | 40 |  |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/2701/0004 | Instrument Datasheet - Manual Call Point |  |  | 7650-8550-DS-810-3005 | Deliverable | 3 |  | 34 | 40 |  |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3223/0001 | Instrument Datasheet - Pressure Transmitter | A | EO1 | 7650-8550-DS-810-3006 | Deliverable | 3 |  | 34 | 40 | MS15 |  | AE341000 | FALSE |  | 2022-10-31 | 2022-12-20 | 2023-01-11 | 2022-12-20 | 2023-01-24
C5663/TH34/DSH/3223/0002 | Instrument Datasheet – Pressure Gauge | A | EO1 | 7650-8550-DS-810-3007 | Deliverable | 3 |  | 34 | 40 | MS15 |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 | 2023-01-11 17:58 | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3230/0001 | Instrument Datasheet - Temperature Element with Transmitter and Thermowell | A | EO1 | 7650-8550-DS-810-3008 | Deliverable | 3 |  | 34 | 40 | MS15 |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 | 2023-01-19 | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3230/0002 | Instrument Datasheet - Tank Leak and Cooldown Monitoring Sensors (RTD) | A | EO1 | 7650-8550-DS-810-3009 | Deliverable | 3 | IN - 2 | 34 | 40 | MS15 |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 | 2022-12-22 11:54 | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3236/0001 | Instrument Datasheet - DP Flow Transmitter |  |  | 7650-8550-DS-810-3010 | Deliverable | 3 |  | 34 | 40 | MS15 |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3236/0002 | Instrument Datasheet - Variable Area Flowmeter |  |  | 7650-8550-DS-810-3011 | Deliverable | 3 |  | 34 | 40 | MS15 |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3236/0003 | Instrument Datasheet - Orifice Elements |  |  | 7650-8550-DS-810-3012 | Deliverable | 3 |  | 34 | 40 | MS15 |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH34/DSH/3246/0001 | Instrument Datasheet - Control Valves | 1 | EA1 | 7650-8550-DS-810-3003 | Deliverable | 3 | IN - 2 | 34 | 60 | JM10 |  | AE341000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-10-04 09:46 | 2022-12-20 | 2022-12-20 | 2022-12-23
C5663/TH34/DSH/3264/0001 | Instrument Datasheet- Emergency Pull Button |  |  | 7650-8550-DS-810-3013 | Deliverable | 3 |  | 34 | 40 |  |  | AE342000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH34/HUD/0000/3001 | Instrument Hook-up Drawing for Ethane Refrigerated Tank | B | EO2 | 7650-8550-65-810-3006 | Deliverable | 3 |  | 34 | 80 | KW1 |  | AE340000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-15 | 2022-09-30 | 2023-01-27
C5663/TH34/ILD/3201/0001 | Safety Logic Diagram for Ethane Refrigreated Tank |  |  | 7650-8550-27-810-3001 | Deliverable | 1 |  | 34 | 80 |  |  | AE345000 | FALSE |  | 2023-06-30 | 2023-06-30 |  | 2023-07-31 | 2023-07-31
C5663/TH34/LOD/0000/3001 | Instrument Cable Tray Layout of Ethane Refrigerated Tank | 1 | EA1 | 7650-8550-68-810-3024 | Deliverable | 2 | IN - 2 | 34 | 40 | KW1 |  | AE340000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-27 16:45 | 2022-09-30 | 2022-09-30 | 2022-10-21 14:15
C5663/TH34/LOD/3045/3001 | Telecom Equipment (CCTV & PAGA) Layout Drawing of Ethane Refrigerated Tank | 1 | EA1 | 7650-8540-80-810-3020 | Deliverable | 2 | IN - 1 | 34 | 40 | KW1 |  | AE340000 | FALSE |  | 2022-09-15 | 2022-09-15 | 2022-09-21 11:34 | 2022-09-30 | 2022-12-23 | 2022-12-01 15:48
C5663/TH34/LOD/3201/0001 | Layout Drawing Process Monitoring Graphics for Ethane Refrigerated Tank |  |  | 7650-8550-64-810-3001 | Deliverable | 2 |  | 34 | 40 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/TH34/LST/3200/0001 | Instrument List of Ethane Refrigerated Tank | B | EO2 | 7650-8550-60-810-3012 | Deliverable | 2 | IN - 2 | 34 | 40 | JM10 |  | AE346000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 20:30 | 2023-08-31 | 2023-08-31
C5663/TH34/LST/3200/0002 | Instrument I/O List of Ethane Refrigerated Tank | B | EO2 | 7650-8550-60-810-3014 | Deliverable | 2 | IN - 2 | 34 | 40 | JM10 |  | AE346000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-30 20:30 | 2023-08-31 | 2023-08-31
C5663/TH34/LST/3258/3001 | Instrument Cable List of Ethane Refrigerated Tank | A | EO1 | 7650-8550-IN-810-3016 | Deliverable | 2 | IN - 2 | 34 | 80 | JM10 |  | AE346000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-09-29 16:02 | 2023-08-31 | 2023-08-31
C5663/TH34/RPT/0080/0002 | Alarm Rationalisation Report |  |  | 7650-8550-RP-810-3002 | Deliverable | 2 |  | 34 | 24 |  |  | AE361000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/TH34/RPT/3200/0001 | SIL Verification Report |  |  | 7650-8550-RP-810-3007 | Deliverable | 2 |  | 34 | 80 |  |  | AE343000 | FALSE |  | 2022-12-20 | 2022-12-20 |  | 2023-06-30 | 2023-06-30
C5663/TH34/TAD/3200/0001 | Standard Support for Instruments |  |  | 7650-8550-68-810-3001 | Deliverable | 2 |  | 34 | 40 |  |  | AE347000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-10-31 | 2023-10-31
C5663/TH34/TCN/3200/0001 | General Description of Instrumentation System for Ethane Refrigerated Tank | 2 | EA2 | 7650-8550-TN-810-3001 | Deliverable | 1 | IN - 2 | 34 | 25 | JM10 |  | AE340000 | FALSE |  | 2022-07-31 | 2022-07-31 |  | 2022-09-30 | 2022-09-30 | 2022-07-25 18:30
C5663/TH34/TSP/3203/3001 | Safety Requirement Specification (SIF-SRS) for Ethane Refrigerated Tank | A | EO1 | 7650-8550-SP-810-3007 | Deliverable | 2 | IN - 3 | 34 | 180 | JM10 |  | AE343000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-09-28 14:01 | 2023-06-30 | 2023-06-30
C5663/TH34/TSP/3219/0001 | Ethane Refrigerated Tank Level & LTD Monitoring Systems Specification | 1 | EA1 | 7650-8550-SP-810-3002 | Deliverable | 2 | IN - 2 | 34 | 40 | JM10 |  | AE341000 | FALSE |  | 2022-10-31 | 2022-10-31 | 2022-10-14 09:23 | 2022-12-20 | 2022-12-20 | 2022-12-01 17:35
C5663/TH34/TSP/3246/0001 | Control Valves Specification for Ethane Refrigerated Tank | 1 | EA1 | 7650-8550-SP-810-3004 | Deliverable | 2 | IN - 1 | 34 | 25 | JM10 |  | AE340000 | FALSE |  | 2022-07-31 | 2022-07-31 |  | 2022-09-30 | 2022-09-30 | 2022-07-27 19:22
C5663/TH34/TSP/3256/0001 | Technical Specification Inclinometer and Inclinometer Pipes | 1 | EA1 | 7650-8550-SP-810-3006 | Deliverable | 2 | IN - 1 | 34 | 40 | JM10 |  | AE341000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-15 21:27 | 2022-09-30 | 2022-09-30 | 2022-10-25 19:26
C5663/TH35/PHL/0000/0001 | Maintenance Philosophy of Ethane Refrigerated Tank | 1 | EF1 | 7650-8954-PH-810-3001 | Deliverable | 2 |  | 35 | 16 | AM4 |  | AE351000 | TRUE |  | 2022-11-30 | 2022-11-30 | 2022-11-17 10:38 | 2022-12-20 | 2023-01-27 | 2023-01-24 15:49
C5663/TH35/RPT/0000/0001 | Material Selection Report of Ethane Refrigerated Tank | 1 | EF1 | 7650-8440-RP-810-3010 | Deliverable | 2 | IN - 1 | 35 | 24 | AM4 |  | AE351000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-17 10:38 | 2022-12-20 | 2022-12-20 | 2022-12-05 09:07
C5663/TH35/TSP/1802/0001 | In-Tank Pumps Specification | 1 | EA1 | 7650-8410-SP-810-3004 | Deliverable | 2 | IN - 1 | 35 | 4 | PF3 |  | AE350000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-27 19:15 | 2022-09-30 | 2022-09-30 | 2022-09-22 11:13
C5663/TH35/TSP/4401/0001 | Ethane In-tank Pump Hoist Specification | 1 | EA1 | 7650-8470-SP-810-3005 | Deliverable | 2 | IN - 1 | 35 | 4 | PF3 |  | AE350000 | FALSE |  | 2022-07-31 19:15 | 2022-07-31 19:15 | 2022-07-27 19:15 | 2022-09-30 | 2022-09-30 | 2022-09-22 11:13
C5663/TH36/CAE/0000/0001 | Cause and Effects Diagram of Ethane Refrigerated Tank | 1 | EA1 | 7650-8110-24-810-3020 | Deliverable | 1 | IN - 2 | 36 | 16 | TF |  | AE361000 | FALSE |  | 2023-05-31 | 2023-05-31 | 2022-07-25 11:06 | 2023-06-30 | 2023-06-30 | 2022-08-19 15:22
C5663/TH36/CAL/0000/0005 | Tank Capacities and Level Settings (Internal) | 1 |  |  | Internal |  |  | 36 | 4 | YL1 |  |  | FALSE |  | 2022-07-15 08:57 | 2022-07-15 08:57 | 2022-07-15 08:57 | 2022-09-15 | 2022-09-15 | 2022-12-20 10:21
C5663/TH36/DSH/0000/0001 | Tank Pressure Safety Valve Datasheet (Internal) | A |  |  | Internal |  |  | 36 | 8 | YL1 |  |  | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-09-08 10:01
C5663/TH36/DSH/0000/0002 | Tank Vacuum Breaker Datasheet (Internal) | A |  |  | Internal |  |  | 36 | 8 | JB13 |  |  | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-26 12:05 | 2022-09-30 | 2022-09-30
C5663/TH36/DSH/0000/0003 | Tank Wall and Bottom Temperature Sensors | 1 | EA1 | 7650-8110-PD-810-3700 | Deliverable | 2 | IN - 1 | 36 | 4 | JB13 |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-27 12:51 | 2022-09-30 | 2022-09-30 | 2022-09-22 11:22
C5663/TH36/DSH/1802/0001 | Datasheet - Ethane In-tank Transfer Pump OSB-P-1001 A/B/C | 1 | EA1 | 7650-8410-DS-810-3001 | Deliverable | 2 | IN - 1 | 36 | 4 | YL1 |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-02 | 2022-09-30 | 2022-09-30 | 2022-09-13
C5663/TH36/DSH/1802/0002 | Datasheet - Future Ethane In-tank Export Pump OSB-P-1003 A/B | 1 | EA1 | 7650-8410-DS-810-3002 | Deliverable | 2 | IN - 1 | 36 | 4 | YL1 |  | AE360000 | FALSE |  | 2022-01-31 | 2022-01-31 | 2022-08-31 | 2022-09-30 | 2022-09-30 | 2022-09-20
C5663/TH36/LST/0000/0001 | Equipment List for Ethane Refrigerated Tank | 1 | EA1 | 7650-8110-EL-810-3010 | Deliverable | 1 | IN - 1 | 36 | 16 | JB13 |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-18 | 2022-09-30 08:57 | 2022-09-30 08:57 | 2022-08-12 08:57
C5663/TH36/LST/0000/0002 | Utility consumption list | 1 | EA1 | 7650-8110-IN-810-3014 | Deliverable | 2 | IN - 1 | 36 | 4 | JB13 |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2022-09-30 | 2022-09-30 | 2022-09-27 10:38
C5663/TH36/LST/0000/0004 | Alarm, Setpoint and Trip List for Ethane Refrigerated Tank |  |  | 7650-8110-IN-810-3004 | Deliverable | 2 |  | 36 | 16 |  |  | AE361000 | FALSE |  | 2023-05-31 | 2023-05-31 |  | 2023-06-30 | 2023-06-30
C5663/TH36/LST/0000/0011 | List of Relief Valves | 1 | EA1 | 7650-8110-IN-810-3001 | Deliverable | 3 | IN - 1 | 36 | 8 | JB13 |  | AE360000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-08-08 13:31 | 2022-09-30 | 2022-09-30 | 2022-09-02
C5663/TH36/LST/0000/0012 | List of Critical Isolations | 3 | EF1 | 7650-8110-IN-810-3002 | Deliverable | 1 | IN - 1 | 36 | 8 | YL1 |  | AE360000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-15 11:49 | 2022-09-30 | 2022-09-30 | 2022-10-14
C5663/TH36/LST/0000/1004 | Battery Limit Interface Summary for Ethane Refrigerated Tank | 1 | EA1 | 7650-8110-IF-810-3011 | Deliverable | 1 | IN - 1 | 36 | 8 | YL1 |  | AE360000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-13 14:43 | 2022-09-30 | 2022-09-30 | 2022-10-13
C5663/TH36/MAL/0000/0001 | Operating Manual for Ethane Refrigerated Tank |  |  | 7650-8110-OM-810-3015 | Deliverable | 2 |  | 36 | 40 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0001 | Completion Systems List |  |  | 7650-8130-PR-810-3001 | Deliverable | 1 |  | 36 | 8 | TF |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0002 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3002 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0003 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3003 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0004 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3004 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0005 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3005 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0006 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3006 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0007 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3007 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0008 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3008 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0009 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3009 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0010 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3010 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0011 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3011 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PCD/0000/0012 | Precommissioning, Commissioning or Start-Up Procedures for xx |  |  | 7650-8130-PR-810-3012 | Deliverable | 1 |  | 36 | 8 |  |  | AE362000 | FALSE |  | 2023-07-31 | 2023-07-31 |  | 2023-08-31 | 2023-08-31
C5663/TH36/PFD/0000/1001 | Process Flow Diagram Ethane Refrigerated Tank | 2 | ES1 | 7650-8110-20-810-3002 | Deliverable | 1 |  | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-08 | 2022-09-30 15:54 | 2022-09-30 15:54 | 2022-08-01 15:54
C5663/TH36/PFD/0000/1003 | MSD for Ethane Refrigerated Tank | 2 | ES1 | 7650-8110-23-810-3004 | Deliverable | 2 |  | 36 | 16 | JB13 |  | AE360000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-18 13:56 | 2022-09-30 | 2022-09-30 | 2022-09-07
C5663/TH36/PFD/0000/1004 | DPTD for Ethane Refrigerated Tank | 2 | ES1 | 7650-8110-22-810-3003 | Deliverable | 1 |  | 36 | 16 | SS16 |  | AE360000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-18 14:28 | 2022-09-30 | 2022-09-30 | 2022-09-27 16:31
C5663/TH36/PHL/0000/0001 | Isolation Philosophy | 1 | EA1 | 7650-8110-PH-810-3702 | Deliverable | 2 | IN - 1 | 36 | 8 | TF |  | AE360000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-11 09:57 | 2022-09-15 | 2022-09-15 | 2022-08-31 10:29
C5663/TH36/PHL/0000/0002 | Process Control and Safeguarding Narrative of Ethane Refrigerated Tank | 1 | EA1 | 7650-8120-PD-810-3008 | Deliverable | 1 | IN - 2 | 36 | 16 | TF |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-12 08:35 | 2022-09-15 | 2022-09-15 | 2022-09-30 15:49
C5663/TH36/PHL/0000/0003 | Ethane Refrigerated Tank Safety & Vacuum Breaker Valves Sizing Basis | 1 | EA1 | 7650-8110-PD-810-3013 | Deliverable | 2 | IN - 1 | 36 | 16 | TF |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-12 08:40 | 2022-09-15 | 2022-09-15 | 2022-09-28 16:26
C5663/TH36/PHL/0000/0005 | Precommissioning, Commissioning and Start-Up Philosophy of Ethane Refrigerated Tank | 2 | EF1 | 7650-8130-PH-810-3016 | Deliverable | 1 |  | 36 | 8 | TF |  | AE360000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-09 | 2022-09-30 | 2022-09-30 | 2022-11-10 17:03
C5663/TH36/PID/0000/0101 | P&ID - List of P&IDs: Ethane Refrigerated Tank | 2 | ER1 | 7650-8110-25-810-3025 | Deliverable | 1 | IN - 1 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:47 | 2022-07-19 15:47 | 2022-07-19 15:47 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:06
C5663/TH36/PID/0000/2101 | P&ID - Ethane Refrigerated Tank Interfaces | 2 | ER1 | 7650-8110-25-810-3030 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-20 15:54 | 2022-07-20 15:54 | 2022-07-20 15:54 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:06
C5663/TH36/PID/0000/2102 | P&ID - Ethane Refrigerated Tank OSB-TK-1001: Piping | 2 | ER1 | 7650-8110-25-810-3031 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-20 15:54 | 2022-07-20 15:54 | 2022-07-20 15:54 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:06
C5663/TH36/PID/0000/2103 | P&ID - Ethane Refrigerated Tank OSB-TK-1001: Instrument | 2 | ER1 | 7650-8110-25-810-3032 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:42 | 2022-07-19 15:42 | 2022-07-19 15:42 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:06
C5663/TH36/PID/0000/2111 | P&ID - Ethane In-Tank Transfer Pump OSB-P-1001A | 2 | ER1 | 7650-8110-25-810-3033 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:41 | 2022-07-19 15:41 | 2022-07-19 15:41 | 2022-09-15 | 2022-09-15 | 2022-08-18 10:29
C5663/TH36/PID/0000/2121 | P&ID - Ethane In-Tank Transfer Pump OSB-P-1001B | 2 | ER1 | 7650-8110-25-810-3034 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:41 | 2022-07-19 15:41 | 2022-07-19 15:41 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:29
C5663/TH36/PID/0000/2131 | P&ID - Ethane In-Tank Transfer Pump OSB-P-1001C | 2 | ER1 | 7650-8110-25-810-3035 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-20 15:53 | 2022-07-20 15:53 | 2022-07-20 15:53 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:29
C5663/TH36/PID/0000/2141 | P&ID - Ethane In-Tank Export Pump OSB-P-1003A | 2 | ER1 | 7650-8110-25-810-3037 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:07
C5663/TH36/PID/0000/2151 | P&ID - Ethane In-Tank Export Pump OSB-P-1003B | 2 | ER1 | 7650-8110-25-810-3038 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:07
C5663/TH36/PID/0000/6101 | P&ID - Ethane Refrigerated Tank: Thermal Relief/Drain Header | 2 | ER1 | 7650-8110-25-810-3039 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:07
C5663/TH36/PID/0000/7101 | P&ID - Ethane Refrigerated Tank: Nitrogen Distribution | 2 | ER1 | 7650-8110-25-810-3040 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-07-19 15:40 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:07
C5663/TH36/PID/0000/7111 | P&ID - Ethane Refrigerated Tank: Instrument Air Distribution | 2 | ER1 | 7650-8110-25-810-3041 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:39 | 2022-07-19 15:39 | 2022-07-19 15:39 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:08
C5663/TH36/PID/0000/7411 | P&ID - Ethane Refrigerated Tank: Plant Air Distribution | 2 | ER1 | 7650-8110-25-810-3042 | Deliverable | 1 | IN - 2 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:38 | 2022-07-19 15:38 | 2022-07-19 15:38 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:08
C5663/TH36/PID/0000/8101 | P&ID - Ethane Refrigerated Tank: Fire Water Distribution | 2 | ER1 | 7650-8110-25-810-3043 | Deliverable | 1 | IN - 1 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:38 | 2022-07-19 15:38 | 2022-07-19 15:38 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:08
C5663/TH36/PID/0000/8102 | P&ID - Ethane Refrigerated Tank: Fire & Gas Detectors | 2 | ER1 | 7650-8110-25-810-3044 | Deliverable | 1 | IN - 1 | 36 | 8 | SS16 |  | AE360000 | FALSE |  | 2022-07-19 15:37 | 2022-07-19 15:37 | 2022-07-19 15:37 | 2022-09-30 | 2022-09-30 | 2022-08-18 10:08
C5663/TH36/TCN/0000/0001 | Process Design Basis for Ethane Refrigerated Tank | 2 | EA2 | 7650-8110-PD-810-3001 | Deliverable | 1 | IN - 1 | 36 | 8 | YL1 |  | AE360000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-11 09:27 | 2022-09-30 | 2022-09-30 | 2022-08-30 20:29
C5663/TH36/TCN/0000/0002 | Process Guarantees | A | EO1 | 7650-8110-TN-810-3001 |  |  |  | 36 | 8 | TF |  |  | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-26 15:04 | 2022-09-30 | 2022-09-30
C5663/TH36/TCN/0000/0003 | Relief and Blowdown Summary of Refrigerated Tanks | 1 | EA1 | 7650-8110-PD-810-3012 | Deliverable | 2 | IN - 1 | 36 | 24 | TF |  | AE360000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-06 08:39 | 2022-09-30 | 2022-09-30 | 2022-09-28 13:58
C5663/TH36/TCN/0000/0004 | Heat and material balance | 1 | EA1 | 7650-8110-20-810-3005 | Deliverable | 1 | IN - 1 | 36 | 24 | TF |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-20 15:51 | 2022-09-30 | 2022-09-30 | 2022-09-20 11:54
C5663/TH36/TCN/0000/0005 | Surge Analysis for Ethane Refrigerated Tank | A | EO1 | 7650-8110-TN-810-3002 | Deliverable | 2 | IN - 2 | 36 | 200 | HG |  | AE360000 | FALSE |  | 2022-09-30 | 2022-09-30 | 2022-09-19 09:20 | 2022-09-30 | 2023-03-31
C5663/TH36/TCN/0000/1002 | Process Description for Ethane Refrigerated Tank | 1 | EA1 | 7650-8110-PD-810-3006 | Deliverable | 2 | IN - 1 | 36 | 8 | JB13 |  | AE360000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-07-11 09:27 | 2022-09-30 08:41 | 2022-09-30 08:41 | 2022-08-12 08:41
C5663/TH36/TSP/0000/1001 | Pressure and Level Control Design Data of Ethane Refrigerated Tank | 2 | EA2 | 7650-8110-PD-810-3007 | Deliverable | 2 | IN - 1 | 36 | 8 | YL1 |  | AE360000 | FALSE |  | 2022-07-25 15:09 | 2022-07-25 15:09 | 2022-07-25 15:09 | 2022-09-30 | 2022-09-30 | 2022-09-15 16:39
C5663/TH38/ADW/0000/0001 | Fire & Gas Detector Layout of Ethane Refrigerated Tank | 1 | EA1 | 7650-8550-61-810-3022 | Deliverable | 1 | IN - 1 | 38 | 16 | SS16 |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-08-26 10:49 | 2022-09-30 | 2022-09-30 | 2022-11-17
C5663/TH38/ADW/0000/0004 | Fire Protection Layout of Ethane Refrigerated Tank | 1 | ES1 | 7650-8140-29-810-3062 | Deliverable | 1 | IN - 1 | 38 | 16 | ZA |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-16 | 2022-09-30 | 2022-09-30 | 2022-11-10
C5663/TH38/ADW/2100/0003 | Emergency Escape Route Plan of Ethane Refrigerated Tank | 1 | ES1 | 7650-8150-29-810-3011 | Deliverable | 2 | IN - 1 | 38 | 8 | ZA |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-16 | 2022-09-30 | 2022-09-30 | 2022-10-25
C5663/TH38/CAE/0000/0021 | Fire and Gas Cause and Effects Diagram of Ethane Refrigerated Tank | 1 | EA1 | 7650-8140-24-810-3021 | Deliverable | 2 | IN - 2 | 38 | 8 | AW5 |  | AE380000 | FALSE |  | 2022-08-31 11:23 | 2022-08-31 11:23 | 2022-08-17 | 2022-09-30 | 2022-09-30 | 2022-11-18
C5663/TH38/DSH/2103/0001 | Datasheet - Portable Fire Extinguishers | A | EO1 | 7650-8140-DS-810-3001 | Deliverable | 2 | IN - 1 | 38 | 8 | ZA |  | AE381000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-28 | 2022-12-21 | 2023-01-27
C5663/TH38/DWG/0000/1012 | Hazardous Area Classification Drawing of Ethane Refrigerated Tank | 1 | ES1 | 7650-8530-71-810-3003 | Deliverable | 2 | IN - 1 | 38 | 16 | ZA |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-26 | 2022-09-30 | 2022-09-30 | 2022-10-25
C5663/TH38/DWG/2100/0003 | Fire Hazard Zone Plan for Ethane Refrigerated Tank | 1 | ES1 | 7650-8140-29-810-3004 | Deliverable | 2 | IN - 1 | 38 | 16 | ZA |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-27 16:45 | 2022-09-30 | 2022-09-30 | 2022-11-10
C5663/TH38/LST/0000/0001 | Emissions, Effluents and Waste Schedule of Ethane Refrigerated Tank | 1 | EF1 | 7650-8150-PH-810-3002 | Deliverable | 2 | IN - 1 | 38 | 8 | ZA |  | AE382000 | FALSE |  | 2023-03-31 | 2023-03-31 | 2022-12-02 13:05 | 2023-04-28 | 2023-04-28 | 2022-12-22
C5663/TH38/LST/0000/0002 | List of Safety Critical Elements for Ethane Refrigerated Tank | 3 | EA3 | 7650-8150-IN-810-3002 | Deliverable | 1 |  | 38 | 48 | ZA |  | AE381000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-10-28 | 2022-12-21 | 2022-12-21 | 2022-11-21 14:16
C5663/TH38/LST/0000/0003 | Functional Safety Register for Ethane Refrigerated Tank |  |  | 7650-8150-IN-810-3003 | Deliverable | 2 |  | 38 | 40 |  |  | AE343000 | FALSE |  | 2022-12-20 | 2022-12-20 |  | 2023-06-30 | 2023-06-30
C5663/TH38/PCD/0000/0001 | Functional Safety Management Plan for Ethane Refrigerated Tank | A | EO1 | 7650-8550-PR-810-3001 | Deliverable | 1 | IN - 3 | 38 | 8 | AW5 |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-22 13:25 | 2022-09-30 | 2023-01-30
C5663/TH38/PHL/0000/0001 | HSE Design Philosophy for Ethane Refrigerated Tank | 1 | EA1 | 7650-8150-PH-810-3001 | Deliverable | 2 | IN - 1 | 38 | 8 | ZA |  | AE380000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 | 2022-09-30 | 2022-09-30 | 2022-09-15 16:30
C5663/TH38/PPL/0000/0001 | Project HSE Design Plan for Ethane Refrigerated Tank | 1 | EA1 | 7650-8150-PL-810-3001 | Deliverable | 2 | IN - 1 | 38 | 8 | AW5 |  | AE380000 | FALSE |  | 2022-07-31 | 2022-07-31 | 2022-07-28 | 2022-09-30 | 2022-09-30 | 2022-09-21 21:39
C5663/TH38/RPT/0000/0001 | Fire and Gas Hazard Assessment Review Report of Ethane Refrigerated Tank | 1 | EA1 | 7650-8140-RP-810-3004 | Deliverable | 2 | IN - 2 | 38 | 8 | ZA |  | AE380000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-26 | 2022-09-30 | 2022-09-30 | 2022-10-04 20:57
C5663/TH38/RPT/0000/0010 | Noise Allocation Report of Ethane Refrigerated Tank | A | EO1 | 7650-8440-RP-810-3018 | Deliverable | 1 | IN - 2 | 38 | 8 | AW5 |  | AE382000 | FALSE |  | 2023-03-31 | 2023-03-31 | 2022-12-13 12:56 | 2023-04-28 | 2023-04-28
C5663/TH38/RPT/0000/0012 | Consequence Modelling Report for Ethane Refrigerated Tank | 1 | EA1 | 7650-8150-ST-810-3001 | Deliverable | 2 | IN - 1 | 38 | 24 | AW5 |  | AE380000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-08-26 19:44 | 2022-09-30 | 2022-09-30 | 2022-09-29 11:35
C5663/TH38/RPT/0000/0013 | Hazardous Area Review Report of Ethane Refrigerated Tank | 1 | EA1 | 7650-8530-RP-810-3005 | Deliverable | 2 | IN - 1 | 38 | 16 | ZA |  | AE380000 | FALSE |  | 2022-08-31 12:40 | 2022-08-31 12:40 | 2022-08-16 | 2022-09-30 | 2022-09-30 | 2022-10-03 20:39
C5663/TH38/RPT/0080/0001 | 3D Fire and Gas System Mapping Report |  |  | 7650-8150-RP-810-3001 | Deliverable | 2 |  | 38 | 24 |  |  | AE383000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH38/RPT/0080/0002 | HAZOP Report for Ethane Refrigerated Tank | 2 | EF1 | 7650-8150-HR-810-3002 | Deliverable | 1 | IN - 1 | 38 | 24 | AW5 |  | AE380000 | FALSE |  | 2022-08-31 | 2022-08-31 | 2022-09-14 | 2022-09-30 | 2022-09-30 | 2022-10-28 16:43
C5663/TH38/RPT/0080/0003 | SIL / LOPA Report for Ethane Refrigerated Tank | 3 | EF1 | 7650-8150-HR-810-3003 | Deliverable | 1 |  | 38 | 48 | AW5 |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-09-15 16:32 | 2022-09-30 | 2022-09-30 | 2022-11-01 19:51
C5663/TH38/RPT/0080/0004 | SIMOPS Review Report for Ethane Refrigerated Tank |  |  | 7650-8150-RP-810-3004 | Deliverable | 1 |  | 38 | 24 |  |  | AE384000 | FALSE |  | 2023-02-28 | 2023-02-28 |  | 2023-03-31 | 2023-03-31
C5663/TH38/RPT/0080/0006 | Final Process Safety Review Report for Ethane Refrigerated Tank |  |  | 7650-8150-RP-810-3006 | Deliverable | 1 |  | 38 | 24 |  |  | AE381000 | FALSE |  | 2022-11-30 | 2023-01-27 |  | 2022-12-21 | 2023-02-24
C5663/TH38/RPT/0080/0008 | Functional Safety Assessment Report |  |  | 7650-8150-RP-810-3008 | Deliverable | 2 |  | 38 | 80 |  |  | AE343000 | FALSE |  | 2022-12-20 | 2022-12-20 |  | 2023-06-30 | 2023-06-30
C5663/TH38/RPT/0080/0012 | HAZOP Review Action Close Out Report for Ethane Refrigerated Tank | A | EO1 | 7650-8150-RP-810-3012 | Deliverable | 1 | IN - 2 | 38 | 24 | ZA |  | AE381000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-10-07 | 2022-12-21 | 2023-01-27
C5663/TH38/RPT/0080/0013 | SIL / LOPA Review Action Close Out Report for Ethane Refrigerated Tank | A | EO1 | 7650-8150-RP-810-3013 | Deliverable | 1 | IN - 2 | 38 | 24 | ZA |  | AE381000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-10-14 | 2022-12-21 | 2023-01-27
C5663/TH38/TCN/0000/0001 | Fire Protection System Design Basis for Ethane Refrigerated Tank | 1 | EF1 | 7650-8140-TN-810-3061 | Deliverable | 1 |  | 38 | 8 | AW5 |  | AE380000 | FALSE |  | 2022-09-10 | 2022-09-10 | 2022-11-25 10:24 | 2022-09-30 | 2023-01-27 | 2023-01-18 14:30
C5663/TH38/TCN/0000/0002 | HAZOP and LOPA Terms of Reference for Ethane Refrigerated Tank | 1 | EA1 | 7650-8150-TN-810-3015 | Deliverable | 1 | IN - 1 | 38 | 8 | AW5 |  | AE380000 | FALSE |  | 2022-07-29 12:59 | 2022-07-29 12:59 | 2022-07-29 12:59 | 2022-09-30 | 2022-09-30 | 2022-08-19 13:05
C5663/TH38/TCN/0000/0003 | Design Performance Standards for Ethane Refrigerated Tank Safety Critical Elements | 1 | EA1 | 7650-8150-TN-810-3003 | Deliverable | 1 |  | 38 | 80 | ZA |  | AE381000 | FALSE |  | 2022-11-30 | 2022-11-30 | 2022-11-11 14:12 | 2022-12-21 | 2022-12-21 | 2022-12-22